## Sheet1
District | Municipality | Barangay | Program Projects | Classification | Appropriation | Responsible | Duration | Year of Source of Fund | Date Started | Date Completed | Expenditures | Actual Accomplishment | Status | Appropriation left
1st District | Manjuyod | Panciao | Establishment of Additional Three (3) SCAA Detachments (Barangay Panciao, Manjuyod) | Vertical | 500000 | Claire S. Chua | 23 C.D. | 2021 | 44616 |  | 105000 | 0.21 | For Reversion | 395000
1st District | Manjuyod | Bagtic | Concreting of Road in Barangay Bagtic, Manjuyod, Negros Oriental | Horizontal | 5000000 | Planning Division |  | 2023 |  |  |  | 0 | For programming | 5000000
1st District | Bindoy | Poblacion | Improvement of Drainage Canal, Brgy. Poblacion, Bindoy | Horizontal | 1000000 | Raimundo G. Pajo | 41 C.D. | 2019 | 44044 |  | 950000 | 0.95 | For Reversion | 50000
1st District | Bindoy | Batangan | Concreting of Farm to Market Road, Brgy. Batangan, Bindoy | Horizontal | 1000000 | Raimundo G. Pajo | 53.5 C.D. | 2019 | 44044 |  | 950000 | 0.95 | For Reversion | 50000
1st District | Bindoy | Pangalaycayan | Concreting of Farm to Market Road, Brgy. Pangalaycayan, Bindoy | Horizontal | 1000000 | Raimundo G. Pajo | 53.5 C.D. | 2019 | 44044 |  | 950000 | 0.95 | For Reversion | 50000
1st District | Bindoy | Domolog | Additional Appropriation for the Construction of Multipurpose Evacuation Center, Barangay Domolog, Bindoy, Negros Oriental | Vertical | 1000000 | Josephine V. Hassan | 45 C.D. | 2018 | 44616 |  | 900000 | 0.9 | For programming | 100000
1st District | Bindoy | Talaptapan | Concreting of FMR from Junction of Talaptapan Road to Talaptapan Elementary School, Bindoy, Negros Oriental | Horizontal | 5000000 | Planning Division |  | 2023 |  |  | 0 | 0 | For programming | 5000000
1st District | Bindoy | Tinaogan | Completion of Evacuation Center at Brgy. Tinaogan, Mun. of Bindoy, Negros Oriental | Vertical | 4000000 | Planning Division |  | 2023 |  |  | 0 | 0 | For programming | 4000000
1st District | Bindoy | Mantalip | Improvement of Mantalip Reef Building, Bindoy, Negros Oriental | Vertical | 10000000 | Planning Division |  | 2023 |  |  | 0 | 0 | For programming | 10000000
1st District | Bindoy | Tinaogan | Construction of Waterworks System, Barangay Tinaogan, Bindoy | Horizontal | 400000 | Raimundo G. Pajo | 85 C.D. | 2015 | 42932 |  | 100000 | 0.25 | For Reversion | 300000
1st District | Bindoy | Tinaogan | Construction of water works system of Tinaogan, Bindoy to Mantalip Reef | Horizontal | 300000 | Raimundo G. Pajo | 15 C.D. | 2015 |  |  | 0 | 0 | For Reversion | 300000
1st District | Bindoy | Poblacion | Improvement of Evacuation Center, Mun. of Bindoy | Vertical | 400000 | Josephine V. Hassan | 45 CD | 2014 |  |  | 0 | 0 | For implementation | 400000
1st District | Bindoy | Tinaogan | Additional Budget to the 1.5 Million CY 2014 Allocation for the Construction of Evacuation Center at Brgy. Tinaogan, Bindoy | Vertical | 1500000 | Josephine V. Hassan | 97 C.D. | 2015 | 42738 |  | 1410000 | 0.94 | Temp. Suspended | 90000
1st District | Bindoy | Tinaogan | Additional Appropriation for the Construction of Multipurpose Building / Evacuation Center at DLANHS, Barangay Tinaogan, Bindoy, Negros Oriental | Vertical | 3000000 | Josephine V. Hassan | 57 C.D. | 2021 | 44642 | 44743 | 3000000 | 1 | Completed | 0
1st District | Bindoy | Atotes | Improvement of Barangay Health Center, Atotes, Bindoy | Vertical | 400000 | Josephine V. Hassan | 35 C.D. | 2013 | 43493 |  | 380000 | 0.95 | Physically Completed | 20000
1st District | Bindoy | Cabcaban | Additional Appropriation for the Improvement of Barangay Health Center, Barangay Cabcaban, Bindoy | Vertical | 300000 | Josephine V. Hassan |  | 2013 | 42387 |  | 90000 | 0.3 | For Reversion | 210000
1st District | Bindoy | Poblacion | Construction of Breastfeeding Room (Bindoy Dist. Hospital) | Vertical | 200000 | Josephine V. Hassan |  | 2016 | 43493 |  | 64000 | 0.32 | For Reversion | 136000
1st District | Bindoy | Poblacion | Rehabilitation of Comfort Rooms for Women - 15 Units (GAD) Bindoy District Hospital | Vertical | 1500000 | Josephine V. Hassan | 65 C.D. | 2016 | 44593 |  | 1395450 | 0.9303 | On-Going | 104550
1st District | Ayungon | Carol-an | Concreting of a Portion of Carol-an Barangay Road, Ayungon | Horizontal | 1000000 | Claire S. Chua | 44.5 C.D. | 2020 | 44586 |  | 247200 | 0.2472 | Temp. Suspended | 752800
1st District | Ayungon | Poblacion | Improvement of Public Market, Municipality of Ayungon | Vertical | 100000 | Claire S. Chua | 15 CD | 2014 |  |  | 23000 | 0.23 | Temp. Suspended | 77000
1st District | Ayungon | Jandalamanon | Improvement of Multi-Purpose Building / Evacuation Center, Barangay Jandalamanon, Ayungon | Vertical | 300000 | Claire S. Chua | 22 C.D. | 2015 |  |  | 15000 | 0.05 | Temp. Suspended | 285000
1st District | Ayungon | Jandalamon | Improvement of Road, Brgy. Jandalamon, Ayungon, Negros Oriental | Horizontal | 10000000 | Planning Division |  | 2023 |  |  | 0 | 0 | For programming | 10000000
1st District | Ayungon | Atabay-Awaan | Road Concreting: Portion of Poblacion-Atabay-Awaan Road, Ayungon, Negros Oriental | Horizontal | 5000000 | Planning Division |  | 2023 |  |  | 0 | 0 | For programming | 5000000
1st District | Ayungon | Poblacion | Improvement of Ayungon Multi-purpose Building and Crisis/Disaster Evacuation Center, Ayungon | Vertical | 1000000 | Claire S. Chua | 55 C.D. | 2016 | 44120 |  | 300000 | 0.3 | Temp. Suspended | 700000
1st District | Ayungon | Lamigan | Construction of Multi-Purpose Building/Evacuation Center, Lamigan, Ayungon | Vertical | 1000000 | Claire S. Chua | 55 C.D. | 2016 | 44630 |  | 50000 | 0.05 | For implementation | 950000
1st District | Ayungon | Tambo | Construction of Multi-Purpose Building, Tambo, Ayungon | Vertical | 1000000 | Claire S. Chua | 47 C.D. | 2016 | 44428 |  | 648400 | 0.6484 | Temp. Suspended | 351600
1st District | Ayungon | Ayungon-Mabato | a) Improvement/Construction of Day Care Center Ayungon - Mabato Proper | Vertical | 300000 | Josephine V. Hassan | 18 C.D. | 2016 | 44409 |  | 285000 | 0.95 | Physically Completed | 15000
1st District | Ayungon | Tampocon I | Improvement of Multi Purpose Building, Tampocon I, Ayungon | Vertical | 438489 | Josephine V. Hassan | 40 C.D. | 2017 | 43493 |  | 429719.22 | 0.98 | Physically Completed | 8769.78
1st District | Ayungon | Carol-an | Improvement of School Building at Ayungon National High School - Carol-an Extension, Ayungon, Negros Oriental | Vertical | 500000 | Josephine V. Hassan | 31 C.D. | 2020 | 44440 |  | 296250 | 0.5925 | Temp. Suspended | 203750
1st District | Ayungon | Maaslum | Repair and Improvement of Maaslum, Ayungon Health Center | Vertical | 150000 | Josephine V. Hassan | 20 C.D. | 2015 | 42388 |  | 36000 | 0.24 | For Reversion | 114000
1st District | Ayungon | Maaslum | Repair and Improvement of Health Center, Maaslum, Ayungon | Vertical | 598153 | Josephine V. Hassan | 50 C.D. | 2018 |  |  | 0 | 0 | For Reversion | 598153
1st District | Tayasan | Pinalubngan-Guincalaban-Eli | Rehabilitation and Improvement of Pinalubngan - Guincalaban - Eli Provincial Road Section, Tayasan, Negros Oriental | Horizontal | 7000000 | Joshua F. Bromo | 158 C.D. | 2021 | 44645 | 44873 | 7000000 | 1 | Completed | 0
1st District | Tayasan | Pinocawan | Concreting of Pinocawan FMR, Barangay Pinocawan, Tayasan, Negros Oriental | Horizontal | 2000000 | Joshua F. Bromo |  | 2022 |  |  | 0 | 0 | For implementation | 2000000
1st District | Tayasan | Jilabangan | Construction of Spillway across Jilabangan River going to Sitio C.O., Barangay Pindahan, Tayasan, Negros Oriental | Horizontal | 3493979 | Planning Division |  | 2023 |  |  |  | 0 | For programming | 3493978.56
1st District | Tayasan | Bago | Improvement of Road of Bago - Tiki Road, Brgy. Bago, Tayasan, Negros Oriental | Horizontal | 10000000 | Planning Division |  | 2023 |  |  |  | 0 | For programming | 10000000
1st District | Tayasan | Poblacion | Construction of Sea Wall, Barangay Poblacion, Tayasan, Negros Oriental | Horizontal | 7500000 | Planning Division |  | 2023 |  |  |  | 0 | For programming | 7500000
1st District | Tayasan | Dalaupon | Concreting of Dalaupon FMR, Barangay Dalaupon, Tayasan, Negros Oriental | Horizontal | 2000000 | Joshua F. Bromo |  | 2022 |  |  | 0 | 0 | For implementation | 2000000
1st District | Tayasan | Matuog | Construction of Multi-purpose Evacuation Center, Brgy. Matuog, Tayasan, Neg. Or. | Vertical | 2000000 | Josephine V. Hassan | 88 W.D. | 2018 | 44030 |  | 1874800 | 0.9374 | Temp. Suspended | 125200
1st District | Tayasan | Linao | Improvement of Waterworks System, Barangay Linao, Tayasan | Horizontal | 500000 | Joshua F. Bromo | 90 C.D. | 2016 | 44378 |  | 485400 | 0.9708 | Physically Completed | 14600
1st District | Tayasan | Banga | Additional appropriation for the improvement of waterworks system in Brgy. Banga, Tayasan (GAD) | Horizontal | 500000 | Joshua F. Bromo | 30 C.D. | 2019 | 44175 |  | 495150 | 0.9903 | Physically Completed | 4850
1st District | Tayasan | Tambulan | Improvement of waterworks system at Brgy. Tambulan, Tayasan, Neg. Or. (GAD) | Horizontal | 500000 | Joshua F. Bromo | 22 C.D. | 2019 | 44322 |  | 495150 | 0.9903 | Physically Completed | 4850
1st District | Tayasan | Lutay | Additional Appropriation for the Construction of Multi-Purpose Building / Evacuation Center, Lutay, Tayasan | Vertical | 800000 | Josephine V. Hassan | 45 C.D. | 2016 | 44030 | 44281 | 800000 | 1 | Completed | 0
1st District | Tayasan | Lutay | Construction of Evacuation Center/ Multi-Purpose Building, Barangay Lutay, Tayasan | Vertical | 500000 | Josephine V. Hassan | 35 C.D. | 2016 | 44030 | 44281 | 500000 | 1 | Completed | 0
1st District | Tayasan | Tambulan | Construction of Evacuation Center of Sitio Nabilog, Barangay Tambulan, Tayasan | Vertical | 1350000 | Josephine V. Hassan | 102 C.D. | 2018 | 44256 |  | 1026000 | 0.76 | On-Going | 324000
1st District | Tayasan | Saying | Completion of Perimeter Fence at Saying E/S, Tayasan, Negros Oriental | Vertical | 400000 | Josephine V. Hassan |  | 2021 | 44641 |  | 32000 | 0.08 | Temp. Suspended | 368000
1st District | Tayasan | Matuog | Completion of Multi-Purpose Bldg. at Matu-og E/S, Tayasan, Negros Oriental | Vertical | 500000 | Josephine V. Hassan | 40 C.D. | 2021 | 44641 |  | 40000 | 0.08 | Temp. Suspended | 460000
1st District | Tayasan | Nabilog | Construction of seven (7) Breastfeeding Rooms to 7 CPH's Nabilog, Tayasan | Vertical | 133500 | Mae Therese P. Oamilda | 12 C.D. | 2017 |  |  | 0 | 0 | For implementation | 133500
1st District | Jimalalud | Malabago-Banog-Buto | Concreting of Malabago-Banog-Buto Road, Jimalalud | Horizontal | 2000000 | Joshua F. Bromo | 85 WD | 2010 | 42236 |  | 2000000 | 1 | Physically Completed | 0
1st District | Jimalalud | Eli-Owacan | Improvement of Eli - Owacan Road, Jimalalud | Horizontal | 1000000 | Mark M. Pastor | 64 WD | 2014 | 42661 |  | 950400 | 0.9504 | Physically Completed | 49600
1st District | Jimalalud | Banog | Improvement of Road going to Barangay Banog, Jimalalud | Horizontal | 627205 | Joshua F. Bromo | 49 C.D. | 2015 | 44098 |  | 627205 | 1 | Physically Completed | 0
1st District | Jimalalud | Owacan | Rehabilitation / Improvement / Upgrading of Owacan - Guihob Provincial Road, Jimalalud - La Libertad, Negros Oriental | Horizontal | 15000000 | Planning Division |  | 2023 |  |  |  | 0 | For programming | 15000000
1st District | Jimalalud | Owacan | Rehabilitation / Improvement / Upgrading of Guincalaban - Eli - Owacan Provincial Road, Jimalalud, Negros Oriental | Horizontal | 15000000 | Planning Division |  | 2023 |  |  |  | 0 | For programming | 15000000
1st District | Jimalalud | Bangkal | Rehabilitation / Improvement / Upgrading of Jimalalud - Bangkal Provincial Road, Jimalalud, Negros Oriental | Horizontal | 4000000 | Planning Division |  | 2023 |  |  |  | 0 | For programming | 4000000
1st District | Jimalalud | Sitio Cabilinan, Brgy. Bangcal | Improvement of Waterworks System at Sitio Cabilinan, Brgy. Bangcal, Jimalalud, Negros Oriental | Waterworks | 1000000 | Planning Division |  | 2023 |  |  |  | 0 | For programming | 1000000
1st District | Jimalalud | North Poblacion to Camandayon | Construction of River Control at Barangay North Poblacion to Camandayon, Jimalalud, Negros Oriental | Horizontal | 5000000 | Planning Division |  | 2023 |  |  |  | 0 | For programming | 5000000
1st District | Jimalalud | Agutayon-Mahanlud-Owacan | Improvement of Agutayon - Mahanlud - Owacan Road, Jimalalud | Horizontal | 1000000 | Joshua F. Bromo | 59 C.D. | 2015 |  |  | 0 | 0 | For implementation | 1000000
1st District | Jimalalud | Tamao | Improvement of Brgy. Road - Brgy. Tamao, Jimalalud, Neg. Or. | Horizontal | 500000 | Joshua F. Bromo | 44 C.D. | 2016 | 44299 |  | 405000 | 0.81 | For Reversion | 95000
1st District | Jimalalud | South Poblacion-Sampiniton | Improvement of South Poblacion - Sampiniton Road, Jimalalud | Horizontal | 750000 | Mark M. Pastor |  | 2018 | 44096 |  | 743175 | 0.9909 | Physically Completed | 6825
1st District | Jimalalud | Dayoyo | Improvement of Waterworks System, Brgy. Dayoyo, Jimalalud | Horizontal | 500000 | Joshua F. Bromo | 41 CD | 2014 | 43042 |  | 75000 | 0.15 | For Reversion | 425000
1st District | Jimalalud | Owacan | Construction of Waterworks System, Barangay Owacan, Jimalalud | Horizontal | 500000 | Joshua F. Bromo | 35 C.D. | 2015 | 44169 |  | 273250 | 0.5465 | Temp. Suspended | 226750
1st District | Jimalalud | Eli | Improvement of Waterworks System, Barangay Eli, Jimalalud | Horizontal | 400000 | Joshua F. Bromo | 26 C.D. | 2015 | 44293 |  | 321720 | 0.8043 | Temp. Suspended | 78280
1st District | Jimalalud | Apanangon | Installation of Waterworks System at So. Kapayawan, Brgy. Apanangon, Jimalalud | Horizontal | 1000000 | Joshua F. Bromo | 60 C.D. | 2019 | 44512 |  | 621300 | 0.6213 | Temp. Suspended | 378700
1st District | Jimalalud | Dayoyo | Construction of Multipurpose Building to Cater to the Needs of the Elderly, Women Organizations, Disabled Persons and Children in Barangay Dayoyo, Jimalalud | Vertical | 4000000 | Mark M. Pastor | 206 W.D. | 2013 | 42248 |  | 3560000 | 0.89 | Temp. Suspended | 440000
1st District | Jimalalud | Poblacion | Impv't. of a Multi-Purpose Hall, Jimalalud | Vertical | 100000 | Mark M. Pastor | 13 WD | 2014 | 42277 |  | 25000 | 0.25 | Temp. Suspended | 75000
1st District | Jimalalud | Banog | Const. of School Stage at Banog E/S, Jimalalud | Vertical | 100000 | Mark M. Pastor | 16 C.D. | 2015 |  |  | 0 | 0 | Temp. Suspended | 100000
1st District | Jimalalud | Owacan | Construction of Comfort Room in Brgy. Owacan, Jimalalud | Vertical | 100000 | Mark M. Pastor | 20 C.D. | 2015 | 43493 |  | 12000 | 0.12 | For Reversion | 88000
1st District | Jimalalud | Pacuan | Construction of Multipurpose Building, Barangay Pacuan, Jimalalud | Vertical | 500000 | Mark M. Pastor | 31 C.D. | 2016 | 44630 |  | 25000 | 0.05 | For implementation | 475000
1st District | Jimalalud | Agutayon | Construction of Multipurpose Building, Barangay Agutayon, Jimalalud | Vertical | 500000 | Mark M. Pastor | 32 C.D. | 2016 | 44630 |  | 25000 | 0.05 | For implementation | 475000
1st District | Jimalalud | Lacaon | Completion of School Stage at Lacaon E/S Jimalalud, Negros Oriental | Vertical | 300000 | Mark M. Pastor | 18 C.D. | 2020 | 44630 |  | 15000 | 0.05 | For implementation | 285000
1st District | Jimalalud | Banog | Completion of School Stage at Banog E/S Jimalalud, Negros Oriental | Vertical | 350000 | Mark M. Pastor | 19 C.D. | 2020 |  |  | 0 | 0 | Temp. Suspended | 350000
1st District | Jimalalud | South Poblacion | Additional Appropriation for the Construction of a Multipurpose Building / Evacuation Center at Barangay South Poblacion, Jimalalud, Negros Oriental | Vertical | 3000000 | Mark M. Pastor |  | 2021 | 44621 |  | 2097600 | 0.6992 | On-Going | 902400
1st District | Jimalalud | Apanangon | Construction of Health Center, Barangay Apanangon, Jimalalud | Vertical | 600000 | Mark M. Pastor | 52 C.D. | 2016 | 44630 |  | 30000 | 0.05 | Temp. Suspended | 570000
1st District | La libertad | San Jose-Biga-a | Rehabilitation of San Jose-Biga-a Road, La Libertad | Horizontal | 500000 | Mark M. Pastor |  | 2010 | 41582 |  | 425000 | 0.85 | For Reversion | 75000
1st District | La libertad | Bagtic | Improvement of Road in Barangay Bagtic, La Libertad | Horizontal | 294500 | Mark M. Pastor | 39 C. D. | 2012 |  |  | 0 | 0 | For Reversion | 294500
1st District | La libertad | Barangay Talaon to Barangay Aya | Local Road Construction/ Development in Barangay Talaon to Barangay Aya, La Libertad, Negros Oriental | Horizontal | 5000000 | Planning Division |  | 2023 |  |  |  | 0 | For programming | 5000000
1st District | La libertad | Pitogo | Improvement & Rehabilitation of Road, Brgy. Pitogo, La Libertad | Horizontal | 500000 | Mark M. Pastor | 39 C.D. | 2014 |  |  | 0 | 0 | For Reversion | 500000
1st District | La libertad | Aya | Road Concreting, Sitio Ampalali - Sitio Pinaghugasan, Barangay Aya, La Libertad | Horizontal | 2305772 | Mark M. Pastor | 54 C.D. | 2015 | 44594 |  | 1361097.2 | 0.5903 | Temp. Suspended | 944674.8
1st District | La libertad | Aya-Talaon-Pitogo | Road Concreting in Barangay Aya - Talaon - Pitogo, La Libertad, Negros Oriental | Horizontal | 5000000 | Mark M. Pastor |  | 2021 |  |  | 977000 | 0.1954 | Temp. Suspended | 4023000
1st District | La libertad | La Libertad-Pacuan | Rehabilitation and Improvement of La Libertad - Pacuan Provincial Road, La Libertad, Negros Oriental | Horizontal | 4000000 | Mark M. Pastor | 76 C.D. | 2021 | 44643 |  | 400000 | 0.1 | Temp. Suspended | 3600000
1st District | La libertad | Biga-a | Construction of River Control along San Jose River, Barangay Biga-a, La Libertad, Negros Oriental | Horizontal | 7500000 | Mark M. Pastor |  | 2022 |  |  | 0 | 0 | For implementation | 7500000
1st District | La libertad | Pacuan | Construction of seven (7) Breastfeeding Rooms to 7 CPH's Pacuan, La Libertad | Vertical | 133500 | Mae Therese P. Oamilda | 16 C.D. | 2017 |  |  | 0 | 0 | Temp. Suspended | 133500
1st District | Guihulngan | Villegas | Water Works System Project, Sitio Aculang, Barangay Villegas, Guihulngan City | Horizontal | 300000 | Hector P. Sotto | 24 C.D. | 2013 | 44540 |  | 285000 | 0.95 | Physically Completed | 15000
1st District | Guihulngan | Hilaitan - Kasingan - Trinidad | Construction of Reinforced Concrete Deck Girder (RCDG) along Provincial Road Hilaitan - Kasingan - Trinidad, Guihulngan City. Negros Oriental | Horizontal | 4000000 | Planning Division |  | 2023 |  |  |  | 0 | For programming | 4000000
1st District | Guihulngan | Poblacion | Completion of NORSU Dormitory at Guihulngan Campus, Guihulngan City, Negros Oriental | Vertical | 5000000 | Planning Division |  | 2023 |  |  |  | 0 | For programming | 5000000
1st District | Guihulngan | Sandayao | Improvement/Rehabilitation of Brgy. Sandayao Waterworks System, Sandayao, Guihulngan City | Horizontal | 150000 | Hector P. Sotto | 15 CD | 2014 | 44652 |  | 142500 | 0.95 | Physically Completed | 7500
1st District | Guihulngan | Luz Sikatuna | Construction of seven (7) Breastfeeding Rooms to 7 CPH's Luz Sikatuna, Guihulngan City | Vertical | 133500 | Mae Therese P. Oamilda | 18 C.D. | 2017 |  |  | 0 | 0 | For Reversion | 133500
1st District | Vallehermoso | Tagbino-Guba | Concreting of Farm-to-Market Road, Tagbino-Guba Barangay Road (Intermittent Section), Vallehermoso | Horizontal | 2000000 | Raimundo G. Pajo | 66.5 C.D. | 2017 | 44136 |  | 1900000 | 0.95 | Physically Completed | 100000
1st District | Vallehermoso | Bagawines-Cabulihan | Concreting of Local Access Road at Brgy. Bagawines to Brgy. Cabulihan, Vallehermoso, Negros Oriental | Horizontal | 5000000 | Jefferson T. Tuganan | 124 C.D. | 2021 | 44628 | 44923 | 5000000 | 1 | Completed | 0
1st District | Vallehermoso | Poblacion | Construction of New Public Market, Brgy. Poblacion, Vallehermoso | Vertical | 20000000 | Jefferson T. Tuganan | 252 C.D. | 2020 | 44534 |  | 17982000 | 0.8991 | On-Going | 2018000
1st District | Vallehermoso | Poblacion | Additional Appropriation for the construction of Public Market, Poblacion, Vallehermoso, Negros Oriental | Vertical | 5000000 | Planning Division |  | 2023 |  |  |  | 0 | For programming | 5000000
1st District | Canlaon | Mabigo | Concreting of Road, Malvar Street Phase II, Barangay Mabigo, Canlaon City, Negros Oriental | Horizontal | 5000000 | Planning Division |  | 2023 |  |  |  | 0 | For programming | 5000000
1st District | Canlaon | Masulog | Additional Appropriation for the Construction of Multipurpose Evacuation Center, Barangay Masulog, Canlaon City, Negros Oriental | Vertical | 1000000 | Jefferson T. Tuganan | 42 C.D. | 2018 | 44502 |  | 450680 | 0.4507 | On-Going | 549320
1st District | Canlaon | Mabigo | Improvement of Multi Purpose Building, Brgy. Mabigo, Canlaon City | Vertical | 300000 | Jefferson T. Tuganan | 20 C.D. | 2017 |  |  | 0 | 0 | For implementation | 300000
1st District | Canlaon | Bayog | Improvement of Multipurpose Building, Barangay Bayog, Canlaon City | Vertical | 1000000 | Jefferson T. Tuganan | 59 W.D. | 2018 | 44138 |  | 900000 | 0.9 | Temp. Suspended | 100000
1st District | Canlaon | Panubigan | a) Panubigan Proper, Canlaon City | Vertical | 300000 | Jefferson T. Tuganan | 44 C.D. | 2016 | 44131 |  | 294000 | 0.98 | Physically Completed | 6000
1st District | Canlaon | Mabigo | Construction of Multi Purpose Building, Canlaon City District Hospital, Brgy. Mabigo, Canlaon City | Vertical | 10500000 | Jefferson T. Tuganan | 215 C.D. | 2020 | 44502 |  | 7465500 | 0.711 | On-Going | 3034500
1st District | Canlaon | Mabigo | Construction of Multi Purpose Building, Canlaon City District Hospital, Brgy. Mabigo, Canlaon City | Vertical | 10500000 | Jefferson T. Tuganan | 215 C.D. | 2020 |  |  | 7514955 | 0.7157 | On-Going | 2985045
2nd District | Dumaguete | Junob | Concreting of Road, Barangay Junob, Dumaguete City | Horizontal | 1000000 | Shannel A. Vendiola | 63 C.D. | 2020 | 44958 |  | 593500 | 0.5935 | On-Going | 406500
2nd District | Dumaguete | Talay-Cantil-e | Continuance Opening and Construction of Farm to Market Road (from existing PCCP at Gawad Kalinga Housing Site -Junction Talay - Cantil-e Road), Barangays Talay and Cantil-e, Dumaguete City | Horizontal | 20000000 | Shannel A. Vendiola | 474 C.D. | 2021 | 44642 |  | 10971200 | 0.5486 | On-Going | 9028800
2nd District | Dumaguete | Purok Masanagon and Purok Mapailubon, Brgy. Mangnao | Additional Appropriation for the Improvement of Drainage Canal at Purok Masanagon and Purok Mapailubon, Brgy. Mangnao - Canal, Dumaguete City, Negros Oriental | Horizontal | 2100000 | Planning Division |  | 2023 |  |  | 0 | 0 | For programming | 2100000
2nd District | Dumaguete | Capitol Provincial | Rehabilitation / Improvement / Upgrading of Dumaguete - Capitol Provincial Road, Dumaguete City, Negros Oriental | Vertical | 20000000 | Planning Division |  | 2023 |  |  | 0 | 0 | For programming | 20000000
2nd District | Dumaguete | Talay | Rehabilitation / Improvement / Upgrading of PEO - Talay Provincial Road, Dumaguete City, Negros Oriental | Horizontal | 5000000 | Planning Division |  | 2023 |  |  | 0 | 0 | For programming | 5000000
2nd District | Dumaguete | Banica | Construction/Rehabilitation of Flood Control Structures along Banica River, Dumaguete City, Negros Oriental | Horizontal | 5000000 | Planning Division |  | 2023 |  |  | 0 | 0 | For programming | 5000000
2nd District | Dumaguete | Bajumpandan | Additional Appropriation for the Construction of DILG Building at Brgy. Bajumpandan, Dumaguete City, Negros Oriental | Vertical | 5000000 | Planning Division |  | 2023 |  |  | 0 | 0 | For programming | 5000000
2nd District | Dumaguete | Daro | Construction of Drainage Canal at Purok Orchids (near the Chinese Cemetery), Daro, Dumaguete City | Horizontal | 500000 | Shannel A. Vendiola | 24 C.D. | 2021 |  |  | 275000 | 0.55 | On-Going | 225000
2nd District | Dumaguete | Capitol Site | Continuance of the Development and Rehabilitation of Ninoy Aquino Freedom Park, Capitol Site, Dumaguete City | Horizontal | 10000000 | Shannel A. Vendiola | 151 C.D. | 2021 | 44677 |  | 10000000 | 1 | Completed | 0
2nd District | Dumaguete | Camanjac | Improvement of Road Lower Camanjac connecting Motong Road, Barangay Camanjac, Dumaguete City, Negros Oriental | Horizontal | 2100000 | Shannel A. Vendiola |  | 2022 |  |  | 0 | 0 | For implementation | 2100000
2nd District | Dumaguete | Cadawinonan | Continuation of Concreting of Road, Mother Rita Housing Project, Barangay Cadawinonan, Dumaguete City, Negros Oriental | Horizontal | 2300000 | Shannel A. Vendiola |  | 2022 |  |  | 0 | 0 | For implementation | 2300000
2nd District | Dumaguete | Motong | Continuation of the Concreting of Roads, Barangay Motong, Dumaguete City, Negros Oriental | Horizontal | 2300000 | Shannel A. Vendiola |  | 2022 |  |  | 0 | 0 | For implementation | 2300000
2nd District | Dumaguete | Piapi | Improvement of Road and Drainage Canal at Fatima Village (Intermittent Sections), Barangay Piapi, Dumaguete City, Negros Oriental | Horizontal | 2100000 | Shannel A. Vendiola |  | 2022 |  |  | 0 | 0 | For implementation | 2100000
2nd District | Dumaguete | Poblacion | Additional Appropriation for the Improvement of LDRRMD Multipurpose Evacuation and Operation Center | Vertical | 6500000 | Aileen Fe E. Mortillero | 210 C.D. | 2020 | 44139 | 44376 | 6500000 | 1 | Completed | 0
2nd District | Dumaguete | Poblacion | Additional Appropriation for the Improvement of LDRRMD Multipurpose Evacuation and Operation Center | Vertical | 7000000 | Aileen Fe E. Mortillero |  | 2021 |  |  | 6650000 | 0.95 | On-Going | 350000
2nd District | Dumaguete | Camanjac | Construction of Flood Control Dike at Barangay Camanjac, Dumaguete City, Negros Oriental | Horizontal | 2100000 | Shannel A. Vendiola | 96 C.D. | 2022 |  |  | 0 | 0 | For implementation | 2100000
2nd District | Dumaguete | Balugo-Cadawinonan | Construction of Flood Control Dike along Banica River, Balugo - Cadawinonan Area, Dumaguete City, Negros Oriental | Horizontal | 2400000 | Shannel A. Vendiola | 117 C.D. | 2022 |  |  | 0 | 0 | For implementation | 2400000
2nd District | Dumaguete | NOPH | Construction of Wastewater Treatment Facility, NOPH, Dumaguete City | Horizontal | 2000000 | Aileen Fe E. Mortillero |  | 2008 |  |  | 1900000 | 0.95 | Physically Completed | 100000
2nd District | Dumaguete | NOPH | Provision of Waste Water Treatment Facility - NOPH, Dumaguete City | Vertical | 2000000 | Aileen Fe E. Mortillero |  | 2009 |  |  | 1900000 | 0.95 | Physically Completed | 100000
2nd District | Dumaguete | Poblacion | Construction of Waste Water Treatment Facility for the Negros Oriental, Provincial Hospital, Dumaguete City | Vertical | 1074031 | Aileen Fe E. Mortillero |  | 2009 |  |  | 1020329.5 | 0.95 | Physically Completed | 53701.5
2nd District | Dumaguete | Poblacion | Establishment of Women's Crisis Center, Dumaguete City | Vertical | 1000000 | Aileen Fe E. Mortillero | 44 C.D. | 2014 | 44638 | 44734 | 1000000 | 1 | Completed | 0
2nd District | Dumaguete | Poblacion | Completion of Women's Crisis Center, Dumaguete City | Vertical | 3000000 | Aileen Fe E. Mortillero |  | 2015 | 44638 | 44732 | 3000000 | 1 | Completed | 0
2nd District | Dumaguete | Poblacion | Buildings and Other Structures - Office Renovation, Dumaguete City | Vertical | 4000000 | Aileen Fe E. Mortillero | 84 C.D. | 2017 | 44519 | 44587 | 4000000 | 1 | Completed | 0
2nd District | Dumaguete | Poblacion | Buildings and Other Structures - Office Renovation, Dumaguete City | Vertical | 4739600 | Aileen Fe E. Mortillero | 116 C.D. | 2016 | 44519 | 44767 | 4739600 | 1 | Physically Completed | 0
2nd District | Dumaguete | Poblacion | Buildings and Other Structures - (Office Renovation) to include Furniture and Fixtures (Provincial Budget Office) Dumaguete City | Vertical | 1600000 | Shannel A. Vendiola | 25 C.D. | 2017 |  |  | 0 | 0 | For implementation | 1600000
2nd District | Dumaguete | Poblacion | Buildings and Other Structures - Office Renovation, Dumaguete City | Vertical | 2000000 | Aileen Fe E. Mortillero | 73 C.D. | 2017 | 44519 |  | 1899800 | 0.9499 | Temp. Suspended | 100200
2nd District | Dumaguete | Poblacion I | Construction of Multi-purpose Hall, Brgy. Poblacion I, Dumaguete City | Vertical | 2000000 | Aileen Fe E. Mortillero | 84 C.D. | 2016 | 44480 | 44721 | 2000000 | 1 | Completed | 0
2nd District | Dumaguete | Piapi | Construction of Barangay Multi-Purpose Hall, Brgy. Piapi, Dumaguete City | Vertical | 2000000 | Aileen Fe E. Mortillero |  | 2019 |  |  | 0 | 0 | For implementation | 2000000
2nd District | Dumaguete | Poblacion | Construction of Multi-Purpose Covered Court and Evacuation Center 1, Dumaguete City | Vertical | 7500000 | Aileen Fe E. Mortillero |  | 2020 |  |  | 0 | 0 | For implementation | 7500000
2nd District | Dumaguete | Poblacion | Improvement of 1st and 2nd Floor Office Stairs Project - (GAD) Stair Landing Rubber Matting - Php 40,000.00 Stair Nosing, Wall Cladding - Php 150,000.00 | Vertical | 190000 | Aileen Fe E. Mortillero |  | 2020 |  |  | 0 | 0 | For implementation | 190000
2nd District | Dumaguete | Poblacion | Renovation (Main Floor, Mezzanine and Comfort Room) of the Provincial Internal Audit Service Office (PIASO) | Vertical | 2000000 | Shannel A. Vendiola | 93 C.D. | 2021 |  |  | 0 | 0 | For implementation | 2000000
2nd District | Dumaguete | Poblacion | Renovation /Restoration of the Sangguniang Panlalawigan Session Hall Dumaguete City | Vertical | 2000000 | Shannel A. Vendiola |  | 2021 |  |  | 0 | 0 | For implementation | 2000000
2nd District | Dumaguete | Poblacion | Buildings and Other Structures Renovation of Archive Room (PAssO) | Vertical | 2000000 | Shannel A. Vendiola | 94 C.D. | 2022 |  |  | 0 | 0 | For implementation | 2000000
2nd District | Dumaguete | Poblacion | Additional Appropriation for the Construction of Women's Crisis Center at Capitol Site, Dumaguete City - (GAD) | Vertical | 16000000 | Aileen Fe E. Mortillero |  | 2022 |  |  | 0 | 0 | For programming | 16000000
2nd District | Sibulan | Poblacion | Construction of Shoreline Protection - Barangay Poblacion, Sibulan, Negros Oriental | Horizontal | 5500000 | Lance L. Arboleda | 63 C.D. | 2022 |  |  | 0 | 0 | For implementation | 5500000
2nd District | Sibulan | Agan-an | Improvement of Road at Purok 1, Barangay Agan-an, Sibulan, Negros Oriental | Horizontal | 5000000 | Planning Division |  | 2023 |  |  | 0 | 0 | For programming | 5000000
2nd District | Sibulan | Poblacion | Construction of Shoreline Protection - Barangay Poblacion, Sibulan, Negros Oriental | Horizontal | 5000000 | Planning Division |  | 2023 |  |  | 0 | 0 | For programming | 5000000
2nd District | Sibulan | Agan-an | Improvement of Track Oval at NOPPO, Barangay Agan-an, Sibulan, Negros Oriental | Horizontal | 1000000 | Planning Division |  | 2023 |  |  | 0 | 0 | For programming | 1000000
2nd District | Sibulan | Agan-an | Construction of Training Center and Dormitory Building at NOPPO, Brgy. Agan-an, Sibulan, Negros Oriental | Vertical | 10000000 | Planning Division |  | 2023 |  |  | 0 | 0 | For programming | 10000000
2nd District | Sibulan | Magatas | Construction of Concrete Dike, Barangay Magatas, Sibulan, Negros Oriental | Horizontal | 10000000 | Lance L. Arboleda |  | 2022 |  |  | 0 | 0 | For implementation | 10000000
2nd District | Sibulan | Agan-an | Construction of Negros Oriental Police Provincial Office (NOPPO) Grandstand and Roofing of the NOPPO Multipurpose Gym/Basketball Court, Camp Lt. Col. Francisco C. Fernandez, Jr., Barangay Agan-an, Sibulan, Negros Oriental | Vertical | 5000000 | Venus T. Cempron |  | 2021 | 44674 | 44886 | 5000000 | 1 | Completed | 0
2nd District | Sanjose | Sra. Ascion - Naiba | Concreting of Sra. Ascion-Naiba Provincial Road, San Jose (L-2.640) | Horizontal | 200000 | Charmen M. Baculad | 40 C.D. | 2013 |  |  | 0 | 0 | For programming | 200000
2nd District | Sanjose | Tampi - Siapo | Rehabilitation and Improvement of Tampi - Siapo Provincial Road, San Jose, Negros Oriental | Horizontal | 3000000 | Planning Division |  | 2023 |  |  |  | 0 | For programming | 3000000
2nd District | Sanjose | Poblacion | Improvement of Norberto Pareja Park, Poblacion, San Jose, Negros Oriental | Vertical | 5000000 | Planning Division |  | 2023 |  |  |  | 0 | For programming | 5000000
2nd District | Sanjose | Tapon Norte | Construction of Tapon Norte Road, Tapon Norte, San Jose | Horizontal | 7600000 | Venus T. Cempron | 168 C.D. | 2019 | 44678 |  | 7600000 | 1 | Completed | 0
2nd District | Sanjose | Poblacion | Construction of Seawall, Poblacion, San Jose, Negros Oriental | Horizontal | 5000000 | Liezel M. Torres | 96 C.D. | 2022 |  |  | 0 | 0 | For implementation | 5000000
2nd District | Sanjose | Tampi | Improvement of Multi-purpose Building/Evacuation Center, Tampi, San Jose | Vertical | 800000 | Liezel M. Torres | 94 C.D. | 2016 |  |  | 568480 | 0.7106 | On-Going | 231520
2nd District | Amlan | Jugno | Concreting of Road at Barangay Jugno, Amlan, Negros Oriental | Horizontal | 2100000 | Liezel M. Torres | 64 C.D. | 2022 |  |  | 0 | 0 | For implementation | 2100000
2nd District | Amlan | Poblacion | Restoration and Improvement of Amlan Multipurpose / Evacuation Center, Poblacion, Amlan, Negros Oriental | Vertical | 5500000 | Liezel M. Torres | 142 C.D. | 2021 | 44533 | 44902 | 5500000 | 1 | Completed | 0
2nd District | Amlan | Tandayag | Construction of Road at Brgy. Tandayag, Amlan, Negros Oriental | Horizontal | 9500000 | Planning Division |  | 2023 |  |  | 0 | 0 | For programming | 9500000
2nd District | Amlan | Jantianon | Improvement of Road at Brgy. Jantianon, Amlan, Negros Oriental | Horizontal | 4000000 | Planning Division |  | 2023 |  |  | 0 | 0 | For programming | 4000000
2nd District | Amlan | Bio-os | Construction of Bridge at Barangay Bio-os, Amlan, Negros Oriental | Horizontal | 5000000 | Planning Division |  | 2023 |  |  | 0 | 0 | For programming | 5000000
2nd District | Amlan | Jantianon | Improvement of Waterworks System at Brgy. Jantianon, Amlan, Negros Oriental | Waterworks | 9596697 | Planning Division |  | 2023 |  |  | 0 | 0 | For programming | 9596697
2nd District | Amlan | Poblacion | Restoration and Improvement of Amlan Mutipurpose Evacuation Center, Barangay Poblacion, Amlan, Negros Oriental | Vertical | 2100000 | Liezel M. Torres | 80 C.D. | 2022 |  |  | 0 | 0 | For implementation | 2100000
2nd District | Amlan | Silab | Dev't. of Cantalina Falls, Ongon River, Brgy. Silab, Amlan | Vertical | 500000 | Venus T. Cempron | 70 C.D. | 2011 | 44089 |  | 475000 | 0.95 | Physically Completed | 25000
2nd District | Amlan | Bio-os | Improvement of Community Learning Center Bio-os Community Learning Center Amlan | Vertical | 45000 | Liezel M. Torres | 11 C.D. | 2015 |  |  | 0 | 0 | For implementation | 45000
2nd District | Amlan | Jugno | Completion of Perimeter Fence at Aurelio Ibero Memorial E/S, Jugno, Amlan, Negros Oriental | Vertical | 200000 | Venus T. Cempron |  | 2021 |  |  | 0 | 0 | Physically Completed | 200000
2nd District | Tanjay | Pal-ew | Improvement of Road, Barangay Pal-ew, Tanjay City | Horizontal | 500000 | Charmen M. Baculad |  | 2023 | 41821 |  | 50000 | 0.1 | For Reversion | 450000
2nd District | Tanjay | Pal-ew | Improvement of Road from So. Lamwas going to So. Pilipigan, Barangay Pal-ew, Tanjay City | Horizontal | 1000000 | Charmen M. Baculad | 28 C.D. | 2019 | 43540 |  | 500000 | 0.5 | On-Going | 500000
2nd District | Tanjay | Sto. Niño | Concreting of Farm-to-Market Road, So. Busay, Barangay Sto. Niño, Tanjay City | Horizontal | 2535974 | Charmen M. Baculad |  | 2019 | 44417 |  | 1267987.1 | 0.5 | On-Going | 1267986.9
2nd District | Tanjay | Inawasan - Bahian - Sto. Niño - Ali-is | Rehabilitation and Improvement of Inawasan - Bahian - Sto. Niño - Ali-is Provincial Road, Pamplona - Tanjay City, Negros Oriental | Horizontal | 10000000 | Charmen M. Baculad |  | 2021 |  |  | 0 | 0 | For implementation | 10000000
2nd District | Tanjay | Poblacion III | Improvement of Multipurpose Building/Evacuation Center, Barangay Poblacion III, Tanjay City | Vertical | 900000 | Venus T. Cempron | 52 C.D. | 2019 | 44256 |  | 0 | 0 | Physically Completed | 900000
2nd District | Tanjay | Sto. Niño | Construction of Box Culvert Across Tad-tad River at Sitio Tinubuhan, Brgy. Sto. Niño, Tanjay City | Horizontal | 10000000 | Planning Division |  | 2023 |  |  |  | 0 | For programming | 10000000
2nd District | Tanjay | Azagra | Rehabilitation of Farm to Market Road at Sitio Candanqui, Brgy. Azagra, Tanjay City, Negros Oriental | Horizontal | 10000000 | Planning Division |  | 2023 |  |  |  | 0 | For programming | 10000000
2nd District | Tanjay | Sta. Cruz | Construction of Concrete Road from Sitio Calam-isan to Sitio Pandaitan, Brgy. Sta. Cruz Nuevo, Tanjay City, Negros Oriental | Horizontal | 5000000 | Planning Division |  | 2023 |  |  |  | 0 | For programming | 5000000
2nd District | Tanjay | Sto. Niño | Improvement of Waterworks System at Sto. Niño, Tanjay City, Negros Oriental | Waterworks | 3000000 | Planning Division |  | 2023 |  |  |  | 0 | For programming | 3000000
2nd District | Tanjay | Novallas | Installation of Waterworks System at Brgy. Novallas, Tanjay City, Negros Oriental | Waterworks | 10000000 | Planning Division |  | 2023 |  |  |  | 0 | For programming | 10000000
2nd District | Tanjay | Poblacion | Construction of School Stage at Bais City Special Science Elementary School, Tanjay City, Negros Oriental | Vertical | 700000 | Planning Division |  | 2023 |  |  |  | 0 | For programming | 700000
2nd District | Tanjay | Camp Leon Kilat | Construction of Multipurpose Evacuation and Humanitarian Assistance for Disaster Response (HADR) Coordination Center, Camp Leon Kilat, Tanjay City, Negros Oriental | Vertical | 5000000 | Planning Division |  | 2023 |  |  |  | 0 | For programming | 5000000
2nd District | Tanjay | Luca | Electrification of Boardwalk Tourism Site, Barangay Luka, Tanjay City, Negros Oriental | Vertical | 2719921 | Charmen M. Baculad | 60 W.D. | 2018 | 44147 |  | 2257534.4 | 0.83 | Temp. Suspended | 462386.6
2nd District | Tanjay | Pal-ew | Improvement/Rehabilitation of Brgy. Pal-ew Water Tank, Pal-ew, Tanjay City | Vertical | 150000 | Charmen M. Baculad | 30 CD | 2014 | 44058 |  | 64500 | 0.43 | For Reversion | 85500
2nd District | Tanjay | Sta. Cruz Viejo | Construction of Waterworks System at Sta. Cruz Nuevo, Tanjay City | Horizontal | 1000000 | Charmen M. Baculad | 70 C.D. | 2019 | 44256 |  | 700000 | 0.7 | On-Going | 300000
2nd District | Tanjay | Luca | Development of Board Walk Tourism Site, Barangay Luka, Tanjay City | Vertical | 6100000 | Charmen M. Baculad |  | 2010 | 40861 |  | 5856000 | 0.96 | Physically Completed | 244000
2nd District | Tanjay | Luca | Construction of CR at the Board Walk Tourism Site, Barangay Luca, Tanjay City | Vertical | 900000 | Charmen M. Baculad | 72 C.D. | 2010 | 41699 | 44951 | 900000 | 1 | Completed | 0
2nd District | Tanjay | Luca | Repair/Rehabilitation of the Board Walk, Luca, Tanjay City | Vertical | 150000 | Charmen M. Baculad | 15 W.D. | 2018 | 44138 |  | 150000 | 1 | Physically Completed | 0
2nd District | Tanjay | Poblacion 2 | Completion of Multi-purpose Building, Barangay Poblacion 2, Tanjay City | Vertical | 1000000 | Venus T. Cempron | 108 W.D. | 2019 | 44593 |  | 950000 | 0.95 | Physically Completed | 50000
2nd District | Tanjay | Tanjay City | Completion of Pathway at Tanjay National H/S, Tanjay City, Negros Oriental | Vertical | 500000 | Venus T. Cempron | 26 C.D. | 2021 | 44621 |  | 475000 | 0.95 | Physically Completed | 25000
2nd District | Tanjay | Sta. Cruz Viejo | Repair/Rehabilitation/Improvement of the Old Barracks at Camp Leon Kilat, Barangay Sta. Cruz Viejo, Tanjay City, to be converted into a Museum for the Memorabilia of the Negrense Warriors for Peace | Vertical | 5000000 | Marvin Calbog |  | 2021 | 44678 |  | 5000000 | 1 | Physically Completed | 0
2nd District | Pamplona | Fatima-Calicanan | Improvement of Fatima - Calicanan Road, Pamplona | Horizontal | 500000 | Venus T. Cempron | 37 W.D. | 2014 |  |  | 0 | 0 | For Reversion | 500000
2nd District | Pamplona | Calicanan | Concreting of Road, Barangay Calicanan, Pamplona | Horizontal | 500000 | Venus T. Cempron | 37 C.D. | 2016 | 44494 |  | 200000 | 0.4 | For Reversion | 300000
2nd District | Pamplona | Abante | Improvement of Tourism Site (Palaypay Falls), Barangay Abante, Pamplona | Vertical | 5000000 | Venus T. Cempron |  | 2018 |  |  | 1879500 | 0.3759 | On-Going | 3120500
2nd District | Pamplona | Mamburao | Construction of River Dike, So. Hakuton, Barangay Mamburao, Pamplona, Negros Oriental | Horizontal | 2000000 | Venus T. Cempron | 66 C.D. | 2018 | 44314 |  | 1500000 | 0.75 | Temp. Suspended | 500000
2nd District | Pamplona | Banawe | Improvement of Road at Sitio Tigbao, Brgy. Banawe, Pamplona, Negros Oriental | Horizontal | 10000000 | Planning Division |  | 2023 |  |  | 0 | 0 | For programming | 10000000
2nd District | Pamplona | Sitio Macasacasa, Balayong to Barangay Yupisan | Improvement of Road at Sitio Macasacasa, Balayong to Barangay Yupisan, Pamplona, Negros Oriental | Horizontal | 10000000 | Planning Division |  | 2023 |  |  | 0 | 0 | For programming | 10000000
2nd District | Pamplona | Mamburao | Improvement of Road at Barangay Mamburao, Pamplona, Negros Oriental | Horizontal | 10000000 | Planning Division |  | 2023 |  |  | 0 | 0 | For programming | 10000000
2nd District | Pamplona | Banawe | Rehabilitation / Improvement / Upgrading of Brgy. Banawe - So. Tigbao, Banawe - So. Caningay, Banawe, Pamplona - Brgy. Buenavista, Sta. Catalina - Brgy. San Miguel, Sta. Catalina FMR, Pamplona - Sta. Catalina, Negros Oriental | Horizontal | 30000000 | Planning Division |  | 2023 |  |  | 0 | 0 | For programming | 30000000
2nd District | Pamplona | Simborio | Repair / Strengthening / Rehabilitation of Bridge, Brgy. Simborio, Pamplona, Negros Oriental | Horizontal | 45526128 | Planning Division |  | 2023 |  |  | 0 | 0 | For programming | 45526127.99
2nd District | Pamplona | Poblacion | Rehabilitation / Improvement / Upgrading of Crossing Datagon, Pamplona - Magsusunog, Pamplona - E. Villanueva, Sibulan - Calinawan, Sibulan - Inas, Valencia Provincial Road Section, Pamplona - Sibulan & Valencia, Negros Oriental | Horizontal | 30000000 | Planning Division |  | 2023 |  |  | 0 | 0 | For programming | 30000000
2nd District | Pamplona | Poblacion | Additional Appropriation for the Improvement of Pamplona Waterworks System, Pamplona, Negros Oriental | Waterworks | 8000000 | Planning Division |  | 2023 |  |  | 0 | 0 | For programming | 8000000
2nd District | Pamplona | Malalangsi | Construction of River Control at Barangay Malalangsi, Pamplona, Negros Oriental | Horizontal | 3000000 | Planning Division |  | 2023 |  |  | 0 | 0 | For programming | 3000000
2nd District | Pamplona | Malalangsi | Construction of Multi-Purpose Building at Sitio Igbalanac, Barangay Malalangsi, Pamplona, Negros Oriental | Vertical | 5000000 | Planning Division |  | 2023 |  |  | 0 | 0 | For programming | 5000000
2nd District | Pamplona | San Isidro | Construction of Footbridge, Barangay San Isidro, Pamplona, Negros Oriental | Horizontal | 1000000 | Planning Division |  | 2023 |  |  | 0 | 0 | For programming | 1000000
2nd District | Pamplona | Poblacion | Construction of Multipurpose Evacuation Center at Pamplona National H/S, Barangay Poblacion, Pamplona, Negros Oriental | Vertical | 2500000 | Venus T. Cempron |  | 2022 |  |  | 0 | 0 | For implementation | 2500000
2nd District | Pamplona | Malalangsi | Construction of Flood Control Dike, Barangay Malalangsi, Pamplona, Negros Oriental | Horizontal | 3600000 | Venus T. Cempron | 150 C.D. | 2022 |  |  | 0 | 0 | For implementation | 3600000
2nd District | Pamplona | Poblacion | Construction of Waterworks System, Municipality of Pamplona, Negros Oriental | Horizontal | 20000000 | Marvin Calbog |  | 2021 | 44659 |  | 0 | 0 | Temp. Suspended | 20000000
2nd District | Pamplona | Magsusnog | Construction of BADC at Magsusunog, Pamplona | Vertical | 500000 | Venus T. Cempron | 32 C.D. | 2018 | 44315 |  | 475000 | 0.95 | Physically Completed | 25000
2nd District | Pamplona | Poblacion | Construction of Male and Female Comfort Room at Proposed Market Bldg., Pamplona | Vertical | 2000000 | Venus T. Cempron | 96 C.D. | 2018 |  |  | 0 | 0 | For implementation | 2000000
2nd District | Pamplona | Poblacion | Establishment of Additional Three (3) SCAA Detachments (Municipality of Pamplona) | Vertical | 500000 | Josephine V. Hassan | 23 C.D. | 2021 | 44616 |  | 80000 | 0.16 | Temp. Suspended | 420000
2nd District | Bais | Cambagyo | Construction of Box Culvert, Barangay Cambagyo, Bais City | Horizontal | 700000 | Niña Rose S. Sayson | 53 CD | 2013 | 42506 |  | 455000 | 0.65 | For Reversion | 245000
2nd District | Bais | Looc | Construction/Rehabilitation of Multi-purpose Hall at Barangay Looc, Bais City | Vertical | 100000 | Marvin Calbog | 40 C.D. | 2017 | 44682 |  | 98000 | 0.98 | Physically Completed | 2000
2nd District | Bais | Barangay II | Improvement/Rehabilitation of City Streets, Portland Cement Concrete Pavement (PCCP) at Tavera Street, Barangay II, Bais City, Negros Oriental | Horizontal | 5000000 | Planning Division |  | 2023 |  |  |  | 0 | For programming | 5000000
2nd District | Bais | Barangay II | Improvement/Rehabilitation of City Streets, Portland Cement Concrete Pavement (PCCP) at Tavera Street, Barangay II, Bais City, Negros Oriental | Horizontal | 5000000 | Planning Division |  | 2023 |  |  |  | 0 | For programming | 5000000
2nd District | Bais | Poblacion | Repair and Rehabilitation of Damaged Structures / Shoreline Protection at Panambalon Fishery Complex, Bais City | Vertical | 5903392 | Planning Division |  | 2023 |  |  |  | 0 | For programming | 5903391.5
2nd District | Bais | Poblacion | Repair and Rehabilitation of Damaged Structures / Shoreline Protection at Panambalon Fishery Complex, Bais City | Vertical | 5903392 | Planning Division |  | 2023 |  |  |  | 0 | For programming | 5903391.5
2nd District | Bais | Looc | Improvement of Oyster Farm Facilities, Hindungawan, Barangay Looc, Bais City | Vertical | 600000 | Michael A. Teves | 43 C.D. | 2017 | 43777 |  | 600000 | 1 | Physically Completed | 0
2nd District | Bais | Biñohon | Improvement of Multipurpose Building, Sitio Batugan, Barangay Biñohon, Bais City | Vertical | 500000 | Niña Rose S. Sayson | 25 Days | 2017 | 44621 | 45016 | 500000 | 1 | Completed | 0
2nd District | Bais | Poblacion | Construction of Transformer Platform and its Accessories for three (3) units 100KVA Transformer, Bais District Hospital, Bais City | Vertical | 150000 | Michael A. Teves | 16 Days | 2018 | 44635 | 44742 | 150000 | 1 | Completed | 0
2nd District | Bais | Consolacion | Construction of Multipurpose Building at Bais City - Pag-IBIG Housing Project Site, Barangay Consolacion, Bais City | Vertical | 5000000 | Michael A. Teves | 127 Days | 2021 | 44623 | 44795 | 5000000 | 1 | Completed | 0
2nd District | Bais | Poblacion | Construction, Upgrading, Expansion, Repair and Renovation of Bais District Hospital, Bais City, Neg. Or. | Vertical | 3400000 | Michael A. Teves | 228 C.D. | 2018 |  |  | 3400000 | 1 | Completed | 0
2nd District | Mabinay | Pandanon | Opening/Rehabilitation of Barangay Road, Barangay Pandanon, Mabinay | Horizontal | 500000 | Deuben C. Durango, Jr. | 26 WD | 2014 | 42522 |  | 475000 | 0.95 | For Reversion | 25000
2nd District | Mabinay | Mayaposi | Improvement of Road, Barangay Mayaposi, Mabinay | Horizontal | 500000 | Deuben C. Durango, Jr. | 26 WD | 2014 | 42339 |  | 475000 | 0.95 | For Reversion | 25000
2nd District | Mabinay | Pantao | Construction of Box Culvert at Sitio Bulod, Brgy. Pantao, Mabinay, Negros Oriental | Horizontal | 3000000 | Planning Division |  | 2023 |  |  |  | 0 | For programming | 3000000
2nd District | Mabinay | Pantao | Improvement of Road at Sitio Naasog, Brgy. Pantao, Mabinay, Negros Oriental | Horizontal | 1000000 | Planning Division |  | 2023 |  |  |  | 0 | For programming | 1000000
2nd District | Mabinay | Poblacion | Completion of the Dormitory Type Building at Mabinay Spring, Mabinay, Negros Oriental | Vertical | 5000000 | Planning Division |  | 2023 |  |  |  | 0 | For programming | 5000000
2nd District | Mabinay | Poblacion | Construction of Comfort Room at Dahile Provincial Community High School, Mabinay, Negros Oriental | Vertical | 300000 | Planning Division |  | 2023 |  |  |  | 0 | For programming | 300000
2nd District | Mabinay | Canggohob | Construction/Improvement of Road, Barangay Canggohob, Mabinay | Horizontal | 300000 | Deuben C. Durango, Jr. | 16 WD | 2014 | 42296 | 44742 | 300000 | 1 | Completed | 0
2nd District | Mabinay | Inapoy | Improvement of Road at So. Tampa, Brgy. Inapoy, Mabinay, Neg. Or. | Horizontal | 541583 | Deuben C. Durango, Jr. | 35 C.D. | 2015 | 42767 |  | 514503.85 | 0.95 | For Reversion | 27079.15
2nd District | Mabinay | Bugnay | Improvement of Road, Barangay Bugnay, Mabinay | Horizontal | 500000 | Deuben C. Durango, Jr. | 31 C.D. | 2016 | 44470 |  | 475000 | 0.95 | On-Going | 25000
2nd District | Mabinay | New Namangka | Improvement of Brgy. Road - Brgy. New Namangka, Mabinay, Neg. Or. | Horizontal | 400000 | Deuben C. Durango, Jr. | 16 W.D. | 2016 |  |  | 0 | 0 | For Reversion | 400000
2nd District | Mabinay | Lumbangan | Rehabilitation of Road at Lower So. Tilingan, Lumbangan, Mabinay | Horizontal | 500000 | Deuben C. Durango, Jr. | 40 C.D. | 2018 | 43552 |  | 35000 | 0.07 | Temp. Suspended | 465000
2nd District | Mabinay | Inapoy | Additional Appropriation for the Construction of Evacuation Center, Barangay Inapoy, Mabinay | Vertical | 500000 | Deuben C. Durango, Jr. | 26 W.D. | 2017 | 44348 |  | 460000 | 0.92 | On-Going | 40000
2nd District | Mabinay | Lumbangan | Additional Appropriation for the Construction of Multipurpose Evacuation Center, Barangay Lumbangan, Mabinay, Negros Oriental | Vertical | 1000000 | Deuben C. Durango, Jr. | 56 Days | 2018 | 44502 |  | 950000 | 0.95 | On-Going | 50000
2nd District | Mabinay | Campanun-an | Improvement of Multipurpose Evacuation Center, Barangay Campanun-an, Mabinay | Vertical | 1000000 | Deuben C. Durango, Jr. | 40 C.D. | 2018 | 44625 |  | 500000 | 0.5 | On-Going | 500000
2nd District | Mabinay | Bulwang | Additional Appropriation for the Construction of Multi-purpose Evacuation Center, Barangay Bulwang, Mabinay, Neg. Or. | Vertical | 1500000 | Deuben C. Durango, Jr. | 91 Days | 2018 | 44625 |  | 1500000 | 1 | Completed | 0
2nd District | Mabinay | Paniabonan | Improvement of Waterworks System, Barangay Paniabonan, Mabinay | Horizontal | 300000 | Deuben C. Durango, Jr. | 16 C.D. | 2016 | 44418 |  | 285000 | 0.95 | On-Going | 15000
2nd District | Mabinay | Luyang | Construction of Reservoir & Springbox from the Shallow Well of So. Catampaan, Paniabonan to So. Tomonon & Spillway, Brgy. Luyang, Mabinay, Neg. Or. | Horizontal | 500000 | Deuben C. Durango, Jr. | 60 C.D. | 2016 | 44418 |  | 475000 | 0.95 | Physically Completed | 25000
2nd District | Mabinay | Himocdongon | Water System Project, Himocdongon, Mabinay | Horizontal | 2000000 | Deuben C. Durango, Jr. | 197 C.D. | 2016 |  |  | 1920000 | 0.96 | On-Going | 80000
2nd District | Mabinay | Bagtic | Improvement of Waterworks System at So. Mampalasan, Barangay Bagtic, Mabinay, Negros Oriental | Horizontal | 500000 | Deuben C. Durango, Jr. | 30 C.D. | 2018 | 44348 |  | 309550 | 0.6191 | On-Going | 190450
2nd District | Mabinay | Bulwang | Construction/Repair of CR at Bulwang Cave Site, Barangay Bulwang, Mabinay | Vertical | 400000 | Deuben C. Durango, Jr. |  | 2010 | 41344 |  | 252000 | 0.63 | For Reversion | 148000
2nd District | Mabinay | NORSu Campus | Const. of School Pathway @ NORSU Campus, Mabinay | Vertical | 100000 | Deuben C. Durango, Jr. | 43 C.D. | 2015 | 42398 |  | 4000 | 0.04 | For Reversion | 96000
2nd District | Mabinay | Lumbangan | Improvement of Multi-Purpose Building / Evacuation Center, Barangay Lumbangan, Mabinay | Vertical | 500000 | Deuben C. Durango, Jr. | 35 Days | 2015 | 44105 |  | 500000 | 1 | Physically Completed | 0
2nd District | Mabinay | Paniabonan | Improvement of Paniabonan Mabinay Community Learning Center, Mabinay | Vertical | 100000 | Deuben C. Durango, Jr. | 12 Days | 2022 | 44599 |  | 30000 | 0.3 | On-Going | 70000
2nd District | Mabinay | Pantao | Construction of 1 unit 1CL School Building at Lanot E/S, Brgy. Pantao, Mabinay | Vertical | 700000 | Deuben C. Durango, Jr. | 45 C.D. | 2016 |  |  | 0 | 0 | For implementation | 700000
2nd District | Mabinay | Mabinay H/S | Completion of School Building at Mabinay Science H/S, Mabinay | Vertical | 200000 | Deuben C. Durango, Jr. | 15 W.D. | 2016 | 44256 |  | 200000 | 1 | Completed | 0
2nd District | Mabinay | Himocdongon | Improvement of Multi-Purpose Facility in Barangay Himocdongon, Mabinay | Vertical | 400000 | Deuben C. Durango, Jr. | 30 W.D. | 2016 | 44424 |  | 380000 | 0.95 | On-Going | 20000
2nd District | Mabinay | Poblacion | Completion of the Construction of Women's Crisis Center with two (2) Comfort Rooms (GAD) (Mabinay Medicare Hospital) | Vertical | 950000 | Deuben C. Durango, Jr. | 60 C.D. | 2017 | 44652 |  | 950000 | 1 | Completed | 0
2nd District | Mabinay | Inapoy | Additional Appropriation for the Construction of the MP Bldg/Evacuation Center, Inapoy, Mabinay | Vertical | 500000 | Deuben C. Durango, Jr. | 26.5 W.D. | 2017 | 44508 |  | 475000 | 0.95 | Physically Completed | 25000
2nd District | Mabinay | Hagtu | Completion of Multipurpose Hall, Barangay Hagtu, Mabinay, Negros Oriental | Vertical | 500000 | Deuben C. Durango, Jr. | 41 days | 2017 | 44608 |  | 450250 | 0.9005 | On-Going | 49750
2nd District | Mabinay | Poblacion | Completion of Women's Crisis Center (GAD) Mabinay | Vertical | 1800000 | Deuben C. Durango, Jr. | 55 C.D. | 2018 | 44652 |  | 1800000 | 1 | Completed | 0
2nd District | Mabinay | Old Namangka | Completion of Multi-purpose Building, Brgy. Old Namangka, Mabinay | Vertical | 800000 | Deuben C. Durango, Jr. | 39 Days | 2019 | 44424 |  | 800000 | 1 | Completed | 0
2nd District | Mabinay | Tara | Completion of one (1) CL School Building at Tara Provincial Community H/S, Mabinay | Vertical | 200000 | Deuben C. Durango, Jr. | 18 Days | 2019 | 44606 |  | 40000 | 0.2 | On-Going | 160000
2nd District | Mabinay | Poblacion | Completion of the Construction of Women's Crisis Center, Mabinay Medicare Community Hospital | Vertical | 1500000 | Deuben C. Durango, Jr. | 60 Days | 2020 | 44585 |  | 1500000 | 1 | Completed | 0
2nd District | Mabinay | Himocdongon | Completion of School Stage at Himocdongon E/S, Mabinay, Negros Oriental | Vertical | 200000 | Deuben C. Durango, Jr. | 15 C.D. | 2020 | 44424 |  | 190000 | 0.95 | Physically Completed | 10000
2nd District | Mabinay | Mabinay E/S | Completion of School Stage at Pedro Gobuyan Sr. Memorial E/S, Mabinay, Negros Oriental | Vertical | 200000 | Deuben C. Durango, Jr. | 18 C.D. | 2020 | 44606 |  | 190000 | 0.95 | Physically Completed | 10000
2nd District | Mabinay | Lamdas | Construction of Perimeter Fence at Lamdas Elementary School Mabinay, Negros Oriental | Vertical | 500000 | Deuben C. Durango, Jr. | 30 C.D. | 2020 | 44363 |  | 475000 | 0.95 | Physically Completed | 25000
2nd District | Mabinay | Poblacion | Construction in Progress - Buildings & Other Structures (Rehabilitation and Improvement of Covered Pathways and Wating Area, Tiling and Painting of New OPD and Morgue), Mabinay Medicare Community Hospital | Vertical | 500000 | Deuben C. Durango, Jr. | 19 C.D. | 2019 | 44613 |  | 445700 | 0.8914 | On-Going | 54300
2nd District | Mabinay | Manlingay | Completion of School Stage at Manlingay H/S, Brgy. Manlingay, Mabinay, Negros Oriental | Vertical | 300000 | Deuben C. Durango, Jr. | 28 C.D. | 2021 | 44613 |  | 294000 | 0.98 | Physically Completed | 6000
2nd District | Mabinay | Tara | Completion of Comfort Room at Danawan E/S, Brgy. Tara, Mabinay, Negros Oriental | Vertical | 300000 | Deuben C. Durango, Jr. | 26 C.D. | 2021 | 44606 |  | 285000 | 0.95 | Physically Completed | 15000
2nd District | Mabinay | Lamdas | Completion of Perimeter Fence at Lamdas E/S, Brgy. Lamdas, Mabinay, Negros Oriental | Vertical | 400000 | Deuben C. Durango, Jr. | 31 C.D. | 2021 | 44613 |  | 384000 | 0.96 | Physically Completed | 16000
2nd District | Mabinay | Luyang & Bagtic | Establishment of Additional Three (3) SCAA Detachments (Barangay Luyang & Bagtic, Mabinay) | Vertical | 500000 | Deuben C. Durango, Jr. | 23 C.D. | 2021 | 44616 |  | 90000 | 0.18 | On-Going | 410000
2nd District | Mabinay | Tara | Additional Appropriation for the Completion of Comfort Room at Danawan E/S. Brgy. Tara, Mabinay | Vertical | 200000 | Deuben C. Durango, Jr. | 21 C.D. | 2022 |  |  | 0 | 0 | For implementation | 200000
2nd District | Mabinay | Lamdas | Additional Appropriation for the Completion of Perimeter Fence at Lamdas E/S, Brgy. Lamdas, Mabinay, Negros Oriental | Vertical | 500000 | Deuben C. Durango, Jr. | 31 C.D. | 2022 |  |  | 0 | 0 | For implementation | 500000
2nd District | Mabinay | Poblacion | Completion of X-ray Room, for the Mabinay MCH, Mabinay | Vertical | 300000 | Deuben C. Durango, Jr. |  | 2010 | 41045 |  | 300000 | 1 | Completed | 0
2nd District | Mabinay | Cansal-ing | Repair/Improvement of Cansal-ing Health Center, Cansal-ing, Mabinay | Vertical | 150000 | Deuben C. Durango, Jr. | 20 WD | 2014 | 42257 |  | 12000 | 0.08 | For Reversion | 138000
2nd District | Mabinay | Inapoy | Construction of seven (7) Breastfeeding Rooms to 7 CPH's, Inapoy, Mabinay | Vertical | 133500 | Mae Therese P. Oamilda | 15 C.D. | 2017 |  |  | 0 | 0 | For Reversion | 133500
2nd District | Mabinay | Poblacion | Completion of the Construction of OB-Gyne ER with CR (GAD) Mabinay | Vertical | 200000 | Deuben C. Durango, Jr. | 22 C.D. | 2018 | 44613 |  | 200000 | 1 | Completed | 0
2nd District | Mabinay | Poblacion | Additional Appropriation for the Completion of OB-GYNE Emergency Room with own Comfort Room (GAD, Mabinay Medicare Community Hospital | Vertical | 300000 | Deuben C. Durango, Jr. | 33 C.D. | 2019 |  |  | 0 | 0 | For implementation | 300000
2nd District | Mabinay | Poblacion | Renovation of X-ray Room (with 3-phase electrical connection) at Mabinay Medicare Community Hospital, Mabinay | Vertical | 3000000 | Deuben C. Durango, Jr. | 65 C.D. | 2020 | 44585 |  | 3000000 | 1 | Completed | 0
2nd District | Mabinay | Poblacion | Construction of Newborn Screening (NBS) Hearing Room / Area Mabinay Medicare Community Hospital | Vertical | 500000 | Deuben C. Durango, Jr. |  | 2020 | 44613 |  | 25000 | 0.05 | For implementation | 475000
2nd District | Mabinay | Poblacion | Construction of Isolation Ward/Isolation Nurse's Station (Prefabricated 2 C - Vans 20') with Hallway and Adjacent CR, Mabinay Medicare Community Hospital | Vertical | 700000 | Deuben C. Durango, Jr. | 42 C.D. | 2019 | 44606 |  | 35000 | 0.05 | For implementation | 665000
2nd District | Mabinay | Poblacion | Construction of MMCH Nurse's Quarters Extension Area - (GAD) Mabinay Medicare Community Hospital | Vertical | 800000 | Deuben C. Durango, Jr. | 56 C.D. | 2021 | 44613 |  | 40000 | 0.05 | For implementation | 760000
3rd District | Valencia | Malaunay | Construction of Footbridge at Pulangtubig, Purok Lubi, Barangay Malaunay, Valencia | Horizontal | 1000000 | Maricel M. Salamanes | 41 C.D. | 2020 |  |  | 0 | 0 | For implementation | 1000000
3rd District | Valencia | Palinpinon | Additional Appropriation for the Construction of River Control/Dike connecting Banica River and Tunggo River, Barangay Palinpinon, Valencia | Horizontal | 2000000 | Maricel M. Salamanes | 60 C.D. | 2020 |  |  | 0 | 0 | For implementation | 2000000
3rd District | Valencia | Crossing Datagon - Sta. Agueda - Magsusunog - Enrique Villanueva - Dobdob - Tamlang - Talalak - Nagbagang | Rehabilitation and Improvement of Crossing Datagon - Sta. Agueda - Magsusunog - Enrique Villanueva - Dobdob - Tamlang - Talalak - Nagbagang Provincial Road, Municipalities of Pamplona, Sibulan, Valencia, Sta. Catalina, Negros Oriental | Horizontal | 20000000 | Maricel M. Salamanes |  | 2021 | 44607 | 44681 | 20000000 | 1 | Completed | 0
3rd District | Valencia | Malaunay - Dungga - Inas - Dobdob | Repair/Rehabilitation of the Malaunay - Dungga - Inas - Dobdob Provincial Road, Valencia, Negros Oriental | Horizontal | 4100000 | Maricel M. Salamanes |  | 2021 | 44701 | 44781 | 4100000 | 1 | Completed | 0
3rd District | Valencia | Malaunay | Road Widening and Improvement of So. Talanticon to So. Hayungan Farm-to-Market Road, Barangay Malaunay, Valencia, Negros Oriental | Horizontal | 2500000 | Maricel M. Salamanes |  | 2022 |  |  | 0 | 0 | For implementation | 2500000
3rd District | Valencia | Calinawan | Rehabilitation / Improvement / Upgrading of Crossing Calinawan - Inas Provincial Road, Sibulan - Valencia, Negros Oriental | Horizontal | 10000000 | Planning Division |  | 2023 |  |  |  | 0 | For programming | 10000000
3rd District | Valencia | Tamlang | Rehabilitation / Improvement / Upgrading of Siaton River - Tamlang - Avocado Provincial Road, Valencia and Sta. Catalina, Negros Oriental | Horizontal | 10000000 | Planning Division |  | 2023 |  |  |  | 0 | For programming | 10000000
3rd District | Valencia | Poblacion | Rehabilitation / Improvement / Upgrading of Malaunay - Inas Provincial Road, Valencia, Negros Oriental | Horizontal | 15000000 | Planning Division |  | 2023 |  |  |  | 0 | For programming | 15000000
3rd District | Valencia | Poblacion | Improvement/Rehabilitation of Valencia Waterworks System, Valencia, Negros Oriental | Waterworks | 5000000 | Planning Division |  | 2023 |  |  |  | 0 | For programming | 5000000
3rd District | Valencia | Banica | Construction/Rehabilitation of Flood Control Structures along Banica River, Dumaguete City, Negros Oriental | Horizontal | 5000000 | Planning Division |  | 2023 |  |  |  | 0 | For programming | 5000000
3rd District | Valencia | Balili | Improvement of Road at Brgy. Balili, Valencia, Negros Oriental | Horizontal | 5000000 | Maricel M. Salamanes | 141 C.D. | 2022 |  |  | 0 | 0 | For Reversion | 5000000
3rd District | Valencia | Bongbong | Improvement of Drainage Canal, Purok Aster, Barangay Bongbong, Valencia, Negros Oriental | Horizontal | 5000000 | Maricel M. Salamanes |  | 2022 |  |  | 0 | 0 | For implementation | 5000000
3rd District | Valencia | Malaunay | Construction of River Control at Purok Lubi, Brgy. Malaunay, Valencia, Neg. Or. | Horizontal | 1000000 | Maricel M. Salamanes | 63 C.D. | 2018 | 44410 |  | 250000 | 0.25 | Temp. Suspended | 750000
3rd District | Valencia | Malabo | Construction of River Control, Barangay Malabo, Valencia, Neg. Or. | Horizontal | 3000000 | Maricel M. Salamanes | 73 C.D. | 2020 | 44457 | 44617 | 0 | 0 | Completed | 3000000
3rd District | Valencia | Cambucad | Installation/rehabilitation of street lighting system in Brgy. Cambucad, Valencia | Horizontal | 50000 | Maricel M. Salamanes |  | 2017 |  |  | 0 | 0 | Completed | 50000
3rd District | Valencia | Mampas | Installation/rehabilitation of street lighting system in Brgy. Mampas, Valencia | Horizontal | 50000 | Maricel M. Salamanes |  | 2017 |  |  | 0 | 0 | For Reversion | 50000
3rd District | Valencia | Mampas | Rehabilitation of Water Supply System, Barangay Mampas, Valencia | Horizontal | 150000 | Maricel M. Salamanes | 20 CD | 2014 | 42345 |  | 33000 | 0.22 | For Reversion | 117000
3rd District | Valencia | Poblacion | Improvement of Valencia Waterworks System, Valencia, Negros Oriental | Horizontal | 5000000 | John Rey C. Toledo |  | 2022 |  |  | 0 | 0 | For implementation | 5000000
3rd District | Valencia | Poblacion | Construction of Valencia Multipurpose Hall, Poblacion, Valencia, Negros Oriental | Vertical | 5000000 | Maricel M. Salamanes | 156 C.D. | 2021 | 44529 | 44946 | 5000000 | 1 | Completed | 0
3rd District | Valencia | South Poblacion | Construction of Legislative Building, South Poblacion, Valencia, Negros Oriental (Design and Build) | Vertical | 20000000 | Maricel M. Salamanes | 560 C.D. | 2022 |  |  | 0 | 0 | For Reversion | 20000000
3rd District | Valencia | Dobdob | Construction of Tamlang Valley Community Primary Hospital, Brgy. Dobdob, Valencia, Negros Oriental | Vertical | 20000000 | Michael A. Teves |  | 2021 | 44635 |  | 1278000 | 0.0639 | On-Going | 18722000
3rd District | Bacong | Buntis-Calangag | Barangay Road Concreting, Buntis-Calangag Road, Bacong | Horizontal | 700000 | Maricel M. Salamanes | 50 C.D. | 2018 |  |  | 0 | 0 | For implementation | 700000
3rd District | Bacong | Poblacion | Construction of Seawall, West Poblacion, Bacong, Negros Oriental | Horizontal | 5000000 | Planning Division |  | 2023 |  |  |  | 0 | For programming | 5000000
3rd District | Bacong | West Poblacion | Construction of Seawall, West Poblacion, Bacong, Negros Oriental | Horizontal | 5000000 | Maricel M. Salamanes | 131 C.D. | 2022 |  |  | 0 | 0 | For implementation | 5000000
3rd District | Dauin | Masaplod-Baslay | Rehabilitation and Improvement of Masaplod - Baslay Provincial Road, Dauin, Negros Oriental | Horizontal | 12000000 | Marjolyn D. Morales | 165 C.D. | 2021 | 44566 | 44976 | 12000000 | 1 | Completed | 0
3rd District | Dauin | Lipayo | Construction of Multipurpose Hall/Evacuation Center, Lipayo, Dauin, Neg. Or. | Vertical | 500000 | Mae Therese P. Oamilda | 53 C.D. | 2016 | 43862 |  | 500000 | 1 | Completed | 0
3rd District | Dauin | Poblacion | Rehabilitation / Improvement / Upgrading of Masaplod - Baslay Provincial Road, Dauin, Negros Oriental | Horizontal | 10000000 | Planning Division |  | 2023 |  |  |  | 0 | For programming | 10000000
3rd District | Dauin | Casile | Additional fund for the Concreting of Tunga-Tunga - Casile Brgy. Road, Mun. of Dauin, Negros Oriental | Horizontal | 5000000 | Planning Division |  | 2023 |  |  |  | 0 | For programming | 5000000
3rd District | Dauin | Poblacion | Improvement of Waterworks System, Dauin, Negros Oriental | Waterworks | 10000000 | Planning Division |  | 2023 |  |  |  | 0 | For programming | 10000000
3rd District | Dauin | Baslay | Construction of Multipurpose Evaucation Center, Barangay Baslay, Dauin, Negros Oriental | Vertical | 1000000 | Mae Therese P. Oamilda | 70 C.D. | 2017 | 44075 |  | 980000 | 0.98 | Physically Completed | 20000
3rd District | Dauin | Batuhon Daku | Additional Appropriation for the Construction of Multipurpose Evacuation Center, Batuhon, Daku, Dauin, Negros Oriental | Vertical | 1000000 | Mae Therese P. Oamilda | 70 C.D. | 2017 | 44013 |  | 980000 | 0.98 | Physically Completed | 20000
3rd District | Dauin | Poblacion | Improvement of Waterworks System for the Municipality of Dauin | Horizontal | 20000000 | Liezel M. Torres | 349 C.D. | 2020 | 44247 |  | 20000000 | 1 | Completed | 0
3rd District | Dauin | Poblacion | Improvement of Waterworks System, Dauin (Phase 2) | Horizontal | 10000000 | John Rey C. Toledo | 120 C.D. | 2021 | 44643 |  | 514000 | 0.0514 | Temp. Suspended | 9486000
3rd District | Dauin | Apo | Improvement of Barangay Health Station, Barangay Apo, Dauin | Vertical | 200000 | Mae Therese P. Oamilda | 21 C.D. | 2015 | 44713 |  | 190000 | 0.95 | Physically Completed | 10000
3rd District | Dauin | Baslay | a) Construction of Day Care Center, Baslay, Dauin | Vertical | 350000 | Mae Therese P. Oamilda | 25 C.D. | 2018 | 44044 |  | 339500 | 0.97 | Physically Completed | 10500
3rd District | Dauin | Baslay | Construction of Multi-Purpose/Evacuation Center (Phase I), Brgy. Baslay, Dauin | Vertical | 1000000 | Mae Therese P. Oamilda | 67 C.D. | 2019 | 44166 |  | 960000 | 0.96 | Physically Completed | 40000
3rd District | Dauin | Baslay | Additional Appropriation for the Construction of Multipurpose Building / Evacuation Center at Barangay Baslay, Dauin, Negros Oriental | Vertical | 1500000 | Marjolyn D. Morales | 62 C.D. | 2021 |  |  | 0 | 0 | For implementation | 1500000
3rd District | Dauin | Malongcay Dacu | Construction of School Stage at Malongcay Dacu H/S, Dauin, Negros Oriental | Vertical | 400000 | Mae Therese P. Oamilda | 34 C.D. | 2021 | 44621 |  | 384000 | 0.96 | Physically Completed | 16000
3rd District | Dauin | Bunga | Completion of Multipurpose Covered Court, Barangay Bunga, Dauin, Negros Oriental | Vertical | 3000000 | Marjolyn D. Morales |  | 2022 |  |  | 0 | 0 | For implementation | 3000000
3rd District | Zamboanguita | Poblacion | Concreting of Road Municipal Streets at Barangay Poblacion, Zamboanguita, Negros Oriental | Horizontal | 4000000 | Marjolyn D. Morales | 110 C.D. | 2022 |  |  | 0 | 0 | For implementation | 4000000
3rd District | Zamboanguita | Poblacion | Concreting/Improvement/ Construction of Municipal Streets, Mun. of Zamboanguita, Negros Oriental | Horizontal | 5000000 | Planning Division |  | 2023 |  |  |  | 0 | For programming | 5000000
3rd District | Zamboanguita | Purok 4 | Construction of Box Culvert at Bangculutan River at Purok 4 Connecting Upper Maglinte - Sitio Arabi, Barangay Mayabon, Zamboanguita, Negros Oriental | Horizontal | 10000000 | Planning Division |  | 2023 |  |  |  | 0 | For programming | 10000000
3rd District | Zamboanguita | Purok 4 | Improvement of Road at Purok 4 Connecting Upper Maglinte - Sitio Arabi, Barangay Mayabon, Zamboanguita, Negros Oriental | Horizontal | 5000000 | Planning Division |  | 2023 |  |  |  | 0 | For programming | 5000000
3rd District | Zamboanguita | Najandig | Rehabilitation / Improvement / Upgrading and Opening of Brgy. Najandig, Zamboanguita - Brgy. Tayak, Siaton FMR, Zamboanguita and Siaton, Negros Oriental | Horizontal | 6000000 | Planning Division |  | 2023 |  |  |  | 0 | For programming | 6000000
3rd District | Zamboanguita | Poblacion | Concreting of Municipal Streets, Poblacion, Zambaonguita, Negros Oriental | Horizontal | 5000000 | Marjolyn D. Morales | 115 C.D. | 2022 |  |  | 0 | 0 | For implementation | 5000000
3rd District | Zamboanguita | Mayabon | Construction of River Control connecting the existing footbridge of Sitio Maglinte and Sitio Bangculutan, Brgy. Mayabon, Zamboanguita, Neg. Or. | Horizontal | 2000000 | Marjolyn D. Morales | 81 C.D. | 2018 | 44440 | 44957 | 2000000 | 1 | Completed | 0
3rd District | Zamboanguita | Lutoban | Construction of Multipurpose Hall, Lutoban, Zamboanguita | Vertical | 1000000 | Mae Therese P. Oamilda | 76 C.D. | 2018 | 44138 |  | 950000 | 0.95 | Physically Completed | 50000
3rd District | Siaton | Canaway | Construction of Local Roads in Brgy. Canaway, Siaton | Horizontal | 50000 | Jun Bernard D. Cual | 6 C.D. | 2017 | 43647 |  | 40000 | 0.8 | For Reversion | 10000
3rd District | Siaton | Barangay IV | Construction/Improvement of Drainage Canal along Villanueva Street, Barangay IV, Siaton | Horizontal | 500000 | Jun Bernard D. Cual | 47 C.D. | 2018 | 44228 |  | 67100 | 0.1342 | On-Going | 432900
3rd District | Siaton | Apoloy | Construction of Hanging Footbridge at Tepolo, Barangay Apoloy, Siaton | Horizontal | 3000000 | Jun Bernard D. Cual | 56 C.D. | 2019 | 44618 |  | 27000 | 0.009 | Temp. Suspended | 2973000
3rd District | Siaton | Mantiquil | Road Concreting of So. Cangmamok, Sitio Cuadra and Sitio Sulodpan, Brgy. Mantiquil, Siaton | Horizontal | 2000000 | Jun Bernard D. Cual | 25 C.D. | 2019 | 44630 |  | 1074040 | 0.537 | Temp. Suspended | 925960
3rd District | Siaton | Brgy. 3 | Rehabilitation/Improvement of the Existing Footbridge located along So. Tambol of Brgy. 3, Siaton | Horizontal | 1000000 | Jun Bernard D. Cual | 38 C.D. | 2019 | 44630 |  | 950000 | 0.95 | On-Going | 50000
3rd District | Siaton | Casalaan | Concreting of Road at Barangay Casalaan, Siaton | Horizontal | 5000000 | Jun Bernard D. Cual |  | 2020 |  |  | 0 | 0 | For implementation | 5000000
3rd District | Siaton | Mantiquil | Concreting of Road at Barangay Mantiquil, Siaton | Horizontal | 5000000 | Jun Bernard D. Cual |  | 2020 | 44608 |  | 1927350 | 0.3855 | Temp. Suspended | 3072650
3rd District | Siaton | Mantuyop | Concreting of Barangay Farm-To-Market Road at Purok III, Barangay Mantuyop, Siaton | Horizontal | 1000000 | Jun Bernard D. Cual |  | 2020 | 44523 |  | 1000000 | 1 | Completed | 0
3rd District | Siaton | Napacao | Additional Appropriation for the Construction of Native Chicken Hatchery in Negros Oriental at Siaton Breeding Station, So. Bondo, Brgy. Napacao, Siaton, Negros Oriental | Vertical | 4000000 | Planning Division |  | 2023 |  |  |  | 0 | For programming | 4000000
3rd District | Siaton | Sumaliring | Improvement of Road at Sitio Sumaliring Beach, Brgy. Sumaliring, Siaton, Negros Oriental | Horizontal | 2500000 | Planning Division |  | 2023 |  |  |  | 0 | For programming | 2500000
3rd District | Siaton | Casalaan | Concreting of Road in So. Nawacat, Brgy. Casalaan, Mun. of Siaton, Negros Oriental | Horizontal | 5000000 | Planning Division |  | 2023 |  |  |  | 0 | For programming | 5000000
3rd District | Siaton | Bonawon | Construction of Multiple Box Culvert at Sitio Calangag, Barangay Bonawon, Siaton, Negros Oriental | Horizontal | 15000000 | Planning Division |  | 2023 |  |  |  | 0 | For programming | 15000000
3rd District | Siaton | Poblacion 3 | Improvement of Road, Barangay Poblacion 3, Siaton | Horizontal | 1000000 | Jun Bernard D. Cual |  | 2020 | 44986 |  | 190800 | 0.1908 | On-Going | 809200
3rd District | Siaton | Barangay 3 | Improvement of Drainage System along NORSU Siaton and Siaton National High School Campus, Barangay 3, Siaton, Negros Oriental | Horizontal | 2300000 | Jun Bernard D. Cual |  | 2021 | 44523 |  | 2185000 | 0.95 | On-Going | 115000
3rd District | Siaton | Casalaan | Concreting of Casalaan Barangay Road, Casalaan, Siaton, Negros Oriental (Representing unexpended allocation for Various Socio-Economic Development Projects for the Municipality of Siaton, Negros Oriental - SP Res. # 1153-2020, AO# 41, Series of 2020, 20% DF, CY 2021) | Horizontal | 5000000 | Jun Bernard D. Cual |  | 2021 | 44677 |  | 1711000 | 0.3422 | Temp. Suspended | 3289000
3rd District | Siaton | Mantiquil-Dobdob | Road Improvement from Mantiquil to Dobdob Provincial Road, Siaton -Valencia, Negros Oriental | Horizontal | 5000000 | Jun Bernard D. Cual |  | 2022 |  |  | 0 | 0 | For Reversion | 5000000
3rd District | Siaton | Casalaan | Road Concreting in Barangay Casalaan, Siaton, Negros Oriental | Horizontal | 5000000 | Jun Bernard D. Cual |  | 2022 |  |  | 0 | 0 | For implementation | 5000000
3rd District | Siaton | Casalaan | Concreting of Road at Barangay Casalaan, Siaton, Negros Oriental | Horizontal | 5000000 | Jun Bernard D. Cual |  | 2022 |  |  | 0 | 0 | For implementation | 5000000
3rd District | Siaton | Barangays Quadra and Tayak, Siaton, Barangays Buenavista and Milagrosa, Sta. Catalina | Improvement of CAA Detachments in Barangays Quadra and Tayak, Siaton, Barangays Buenavista and Milagrosa, Sta. Catalina | Vertical | 600000 | Jun Bernard D. Cual | 90 C.D. | 2014 | 43773 |  | 360000 | 0.6 | Temp. Suspended | 240000
3rd District | Siaton | Bonawon | Addt'l. Appropriation for the Const. of Economic Enhancement/Evacuation Center, Bonawon, Siaton, Neg. Or. | Vertical | 1000000 | Jun Bernard D. Cual | 68 C.D. | 2016 | 43409 |  | 959800 | 0.9598 | On-Going | 40200
3rd District | Siaton | Bonawon | Construction of Wave Breaker, Barangay Bonawon, Siaton | Horizontal | 4000000 | Jun Bernard D. Cual | 156 C.D. | 2017 | 43694 |  | 0 | 0 | Temp. Suspended | 4000000
3rd District | Siaton | Bonawon | Additional Appropriation for the Construction of Wave Breaker, Barangay Bonawon, Siaton, Negros Oriental | Vertical | 4000000 | Jun Bernard D. Cual | 126 C.D. | 2017 | 43694 |  | 0 | 0 | Temp. Suspended | 4000000
3rd District | Siaton | Mantuyop | Additional Appropriation for the Construction of Flood Control, Barangay Mantuyop, Siaton, Negros Oriental | Vertical | 3000000 | Jun Bernard D. Cual | 102 C.D. | 2021 | 44523 |  | 3000000 | 1 | Completed | 0
3rd District | Siaton | Napacao | Installation and Maintenance of Street Lighting System in Brgy. Napacao, Siaton | Horizontal | 50000 | Jun Bernard D. Cual | 7 W.D. | 2017 | 43160 |  | 4500 | 0.09 | For Reversion | 45500
3rd District | Siaton | Sumaliring | Improvement of Waterworks System, Barangay Sumaliring, Siaton | Horizontal | 300000 | Jun Bernard D. Cual | 47 C.D. | 2016 | 42887 |  | 285000 | 0.95 | For Reversion | 15000
3rd District | Siaton | Siit | Construction of Water System at Sitio Tala-Tala, Brgy. Siit, Siaton | Horizontal | 1000000 | Jun Bernard D. Cual | 80 C.D. | 2019 | 44470 |  | 906000 | 0.906 | On-Going | 94000
3rd District | Siaton | Bonawon | Rehabilitation of Water System of Barangay Bonawon, Siaton | Horizontal | 2000000 | Jun Bernard D. Cual | 60 C.D. | 2019 | 44287 |  | 1980000 | 0.99 | On-Going | 20000
3rd District | Siaton | Tayak | Construction/Rehabilitation of Tayak Waterworks System, Siaton | Horizontal | 150000 | Jun Bernard D. Cual | 15 C.D. | 2019 | 44105 |  | 76650 | 0.511 | For Reversion | 73350
3rd District | Siaton | Balanan | Construction/Improvement/Rehabilitation of Sandulot Balanan, Siaton Health Center | Vertical | 150000 | Jun Bernard D. Cual | 48 C.D. | 2015 | 44112 |  | 88500 | 0.59 | Temp. Suspended | 61500
3rd District | Siaton | Siit | Construction of Multi-Purpose Building at Sitio Polo, Siit, Siaton | Vertical | 3000000 | Jun Bernard D. Cual | 138 C.D. | 2017 |  |  | 0 | 0 | For Reversion | 3000000
3rd District | Siaton | Poblacion IV | Construction/rehabilitation of Brgy. multi-purpose hall in Brgy. Pob. IV, Siaton | Vertical | 50000 | Jun Bernard D. Cual | 11 C.D. | 2017 | 44120 |  | 33500 | 0.67 | Temp. Suspended | 16500
3rd District | Siaton | Poblacion | Completion of 1CL School Building at Pio Macahig Memorial E/S, Siaton, Negros Oriental | Vertical | 700000 | Jun Bernard D. Cual | 53 C.D. | 2020 | 44380 |  | 692160 | 0.9888 | On-Going | 7840
3rd District | Siaton | Sandulot | Additional Appropriation for the Improvement / Renovation of Balanan Lake Facilities, Barangay Sandulot, Siaton, Negros Oriental | Vertical | 2000000 | Jun Bernard D. Cual | 145 C.D. | 2021 | 44643 |  | 1900000 | 0.95 | On-Going | 100000
3rd District | Siaton | Mantiquil | Completion of 1CL School Bldg. at Mantiquil E/S, Sitio Cuadra, Brgy. Mantiquil, Siaton, Negros Oriental | Vertical | 700000 | Jun Bernard D. Cual | 56 C.D. | 2021 |  |  | 0 | 0 | For Reversion | 700000
3rd District | Siaton | Apoloy | Construction of One (1) unit 1 CL School Building at Apoloy Elementary School, Siaton, Negros Oriental (Reverted from: Const. of One (1) unit 1CL School Bldg. at Estakahan, Siaton, Neg. Or. - Php 762,068.67, Res.# 335, series of 2014 and Add'tl. Approp. - Const. of 1CL School Bldg. at Estakahan, Siaton, Neg. Or. - Php 147,000.00, Res.# 04, series of 2016) | Vertical | 909069 | Jun Bernard D. Cual | 49 C.D. | 2021 |  |  | 0 | 0 | For implementation | 909068.7
3rd District | Siaton | Poblacion | Additional Appropriation for the Completion of 1 unit 1CL School Building at Pio Macahig Memorial E/S, Siaton | Vertical | 500000 | Jun Bernard D. Cual | 39 C.D. | 2022 |  |  | 0 | 0 | For implementation | 500000
3rd District | Siaton | Datag | Completion of Multi-Purpose Hall at Datag E/S, Siaton | Vertical | 900000 | Jun Bernard D. Cual | 55 C.D. | 2022 | 44986 |  | 12420 | 0.0138 | On-Going | 887580
3rd District | Siaton | Poblacion | Construction of Breeding Pen at Provincial Native Chicken Hatchery, Siaton, Negros Oriental | Vertical | 3000000 | Jun Bernard D. Cual | 185 C.D. | 2022 |  |  | 0 | 0 | For Reversion | 3000000
3rd District | Siaton | Sumaliring | Improvement of Health Center, Barangay Sumaliring, Siaton | Vertical | 200000 | Jun Bernard D. Cual | 25 C.D. | 2014 | 44581 |  | 100960 | 0.5048 | On-Going | 99040
3rd District | Siaton | Balanan | Improvement of Barangay Health Station, Balanan, Siaton | Vertical | 100000 | Jun Bernard D. Cual | 15 C.D. | 2016 | 44112 |  | 47000 | 0.47 | Temp. Suspended | 53000
3rd District | Siaton | Poblacion | Construction of Maternity Lodge for Pregnant Mothers on Labor (CLLMMH) | Vertical | 965000 | Jun Bernard D. Cual | 122 W.D. | 2016 | 44136 |  | 347400 | 0.36 | Temp. Suspended | 617600
3rd District | Siaton | Poblacion | Upgrading of Lactation Station (CLLMMH), Siaton | Vertical | 200000 | Jun Bernard D. Cual | 40 C.D. | 2017 |  |  | 0 | 0 | For implementation | 200000
3rd District | Siaton | Poblacion | Repair / Renovation of CLLMMH Delivery Room Cong. Lamberto L. Macias Memorial Hospital, Siaton | Vertical | 200000 | Jun Bernard D. Cual | 16 C.D. | 2021 |  |  | 0 | 0 | For implementation | 200000
3rd District | Sta. Catalina | Nagbalaye | Concreting of Road at So. Mampas, Barangay Nagbalaye, Sta. Catalina | Horizontal | 1000000 | Jun Bernard D. Cual | 52 C.D. | 2019 | 43525 |  | 764500 | 0.7645 | On-Going | 235500
3rd District | Sta. Catalina | Cawitan | Road Concreting Cawitan - Nagbinlod Road, Barangay Cawitan, Sta. Catalina, Negros Oriental | Horizontal | 5000000 | Jun Bernard D. Cual | 90 C.D. | 2021 | 44635 | 44743 | 5000000 | 1 | Completed | 0
3rd District | Sta. Catalina | Poblacion | Rehabilitation / Improvement / Upgrading of Poblacion - Datag - Casala-an - Apoloy, Siaton - So. Tamlang, Sta. Catalina FMR, Siaton, Negros Oriental | Horizontal | 30000000 | Planning Division |  | 2023 |  |  |  | 0 | For programming | 30000000
3rd District | Sta. Catalina | Poblacion | Rehabilitation / Improvement / Upgrading / of San Francisco - Hingles Provincial Road, Sta. Catalina, Negros Oriental | Horizontal | 10000000 | Planning Division |  | 2023 |  |  |  | 0 | For programming | 10000000
3rd District | Sta. Catalina | Poblacion | Rehabilitation / Improvement / Upgrading / of Alangilan - Matanog Provincial Road, Sta. Catalina, Negros Oriental | Horizontal | 10000000 | Planning Division |  | 2023 |  |  |  | 0 | For programming | 10000000
3rd District | Sta. Catalina | Poblacion | Rehabilitation and Improvement of Bonawon - Calangag - Cantiban - San Francisco Road, Siaton and Sta. Catalina, Negros Oriental | Horizontal | 15000000 | Planning Division |  | 2023 |  |  |  | 0 | For programming | 15000000
3rd District | Sta. Catalina | Poblacion | Construction of Footbridge at Sitio Camboong, Barangay San Francisco, Sta. Catalina, Negros Oriental | Horizontal | 3000000 | Planning Division |  | 2023 |  |  |  | 0 | For programming | 3000000
3rd District | Sta. Catalina | Talalak | Construction of Bridge - Reinforced Concrete Deck Gerder (from footbridge to RCDG) between So. Avocado and So. Tamlang, Brgy. Talalak, Sta. Catalina, Negros Oriental | Horizontal | 80979893 | Planning Division |  | 2023 |  |  |  | 0 | For programming | 80979893.45
3rd District | Sta. Catalina | Amio Road | Road Concreting at So. Bunsod, Brgy. Obat to Brgy. Amio Road, Sta. Catalina, Negros Oriental | Horizontal | 5000000 | Planning Division |  | 2023 |  |  |  | 0 | For programming | 5000000
3rd District | Sta. Catalina | San Pedro | Improvement of Waterworks System for Omanod Small Farmers Association (OSFA) at Sitio Omanod, Barangay San Pedro, Sta. Catalina, Negros Oriental | Waterworks | 2000000 | Planning Division |  | 2023 |  |  |  | 0 | For programming | 2000000
3rd District | Sta. Catalina | Amio | Road Concreting, Barangay Obat to Barangay Amio, Sta. Catalina, Negros Oriental | Horizontal | 5000000 | Jun Bernard D. Cual |  | 2022 |  |  | 0 | 0 | For implementation | 5000000
3rd District | Sta. Catalina | Alangilan | Roofing of Multipurpose/Evacuation Center, Alangilan, Sta. Catalina, Negros Oriental | Vertical | 500000 | Jun Bernard D. Cual | 30 C.D. | 2016 | 44986 |  | 11950 | 0.0239 | On-Going | 488050
3rd District | Sta. Catalina | Fatima | Construction of Multi-purpose Evacuation Center, Brgy. Fatima, Sta. Catalina, Neg. Or. | Vertical | 3000000 | Mae Therese P. Oamilda | 136 C.D. | 2018 | 44105 |  | 2910000 | 0.97 | Physically Completed | 90000
3rd District | Sta. Catalina | Milagrosa | Additional Appropriation for the construction of Multi-purpose Evacuation Center, Brgy. Milagrosa, Sta. Catalina, Neg. Or. | Vertical | 1000000 | Mae Therese P. Oamilda | 75 C.D. | 2018 | 44044 |  | 970000 | 0.97 | Physically Completed | 30000
3rd District | Sta. Catalina | Amio | Construction of River Control, Barangay Amio, Sta. Catalina, Negros Oriental | Horizontal | 10000000 | Jun Bernard D. Cual | 300 C.D. | 2021 | 44660 | 44849 | 10000000 | 1 | Completed | 0
3rd District | Sta. Catalina | Poblacion | Improvement of Multipurpose Evacuation Center, Purok 3, Barangay Poblacion, Sta. Catalina, Negros Oriental | Vertical | 2500000 | Jun Bernard D. Cual |  | 2022 |  |  | 0 | 0 | For implementation | 2500000
3rd District | Sta. Catalina | Poblacion | Installation of Street Lighting Project at the Talisay Beach, Brgy. Poblacion, Sta. Catalina | Horizontal | 200000 | Jun Bernard D. Cual |  | 2014 |  |  | 0 | 0 | For Reversion | 200000
3rd District | Sta. Catalina | Poblacion | Construction of Water System within Barangay Poblacion, Sta. Catalina | Horizontal | 550000 | John Rey C. Toledo | 45 C.D. | 2020 |  |  | 0 | 0 | For implementation | 550000
3rd District | Sta. Catalina | Poblacion | Completion of Public Market, Poblacion, Sta. Catalina | Vertical | 3000000 | Mae Therese P. Oamilda | 180 C.D. | 2016 | 43010 |  | 2910000 | 0.97 | Physically Completed | 90000
3rd District | Sta. Catalina | Manggolod | Construction of Perimeter Fence at Manggolod E/S, Brgy. San Jose, Sta. Catalina, Negros Oriental | Vertical | 1180279 | Jun Bernard D. Cual | 73 C.D. | 2021 | 44986 |  | 44260.447 | 0.0375 | On-Going | 1136018.553
3rd District | Sta. Catalina | Poblacion | Establishment of One(1) SCAA Detachment, Sta. Catalina, Negros Oriental | Vertical | 500000 | Jun Bernard D. Cual | 23 C.D. | 2022 |  |  | 0 | 0 | For implementation | 500000
3rd District | Sta. Catalina | Amio | Construction of seven (7) Breastfeeding Rooms to 7 CPH's, Amio, Sta. Catalina | Vertical | 133500 | Mae Therese P. Oamilda | 15 C.D. | 2017 |  |  | 0 | 0 | For Reversion | 133500
3rd District | Sta. Catalina | Talalak | Completion of Health Center at So. Avocado, Barangay Talalak, Sta. Catalina | Vertical | 200000 | Jun Bernard D. Cual | 30 C.D. | 2014 | 44986 |  | 17780 | 0.0889 | On-Going | 182220
3rd District | Bayawan | Banga | Concreting of Road, Barangay Banga, Bayawan City | Horizontal | 800000 | Japhet T. Pinili | 42 C.D. | 2016 | 43988 | 44386 | 800000 | 1 | Completed | 0
3rd District | Bayawan | Ubos | Construction of River Control Dike, Barangay Ubos, Bayawan City | Horizontal | 500000 | Renan A. Enopia | 33 C.D. | 2016 | 43825 |  | 252800 | 0.5056 | Temp. Suspended | 247200
3rd District | Bayawan | San Miguel | Concreting of Road, Barangay San Miguel, Bayawan City | Horizontal | 2000000 | Renan A. Enopia | 81 C.D. | 2019 | 44256 |  | 580000 | 0.29 | Temp. Suspended | 1420000
3rd District | Bayawan | Minaba | Concreting of Road, Barangay Minaba, Bayawan City | Horizontal | 1000000 | Renan A. Enopia | 55 C.D. | 2019 |  |  | 0 | 0 | For Reversion | 1000000
3rd District | Bayawan | Bugay | Additional Appropriation for the Improvement of Road from Proper Bugay going to So. Mabuyag, Barangay Bugay, Bayawan City | Horizontal | 1000000 | Renan A. Enopia | 40 C.D. | 2020 |  |  | 0 | 0 | For implementation | 1000000
3rd District | Bayawan | Tayawan | Construction of Box Culvert at Sitio Guintana-an, Barangay Tayawan, Bayawan City | Horizontal | 5000000 | Renan A. Enopia | 76 C.D. | 2021 |  |  | 29000 | 0.0058 | For implementation | 4971000
3rd District | Bayawan | Bugay | Construction of Flat Slab Bridge at Sitio Caayahan, Brgy. Bugay, Bayawan City | Horizontal | 3000000 | Renan A. Enopia | 58 C.D. | 2019 | 44677 |  | 18300 | 0.0061 | Temp. Suspended | 2981700
3rd District | Bayawan | Poblacion | Rehabilitation / Improvement / Upgrading of Tabuan - Ali-is Provincial Road, Bayawan City, Negros Oriental | Horizontal | 10000000 | Planning Division |  | 2023 |  |  |  | 0 | For programming | 10000000
3rd District | Bayawan | Maninihon | Improvement of Road at Lower Pusi-on, Brgy. Maninihon, Bayawan City, Negros Oriental | Horizontal | 5000000 | Planning Division |  | 2023 |  |  |  | 0 | For programming | 5000000
3rd District | Bayawan | Narra | Improvement of Road at Sitio Terong, Brgy. Narra, Bayawan City, Negros Oriental | Horizontal | 5000000 | Planning Division |  | 2023 |  |  |  | 0 | For programming | 5000000
3rd District | Bayawan | Ubos | Additional Appropriation for the Construction of Flood Control Dike, Barangay Ubos, Bayawan City, Negros Oriental | Horizontal | 3000000 | Renan A. Enopia | 51 W.D. | 2017 | 43988 |  | 1266600 | 0.4222 | Temp. Suspended | 1733400
3rd District | Bayawan | Ubos | Construction of Flood Control, Barangay Ubos, Bayawan City | Horizontal | 2000000 | Renan A. Enopia | 38 C.D. | 2014 | 43825 |  | 1002800 | 0.5014 | Temp. Suspended | 997200
3rd District | Bayawan | Ubos | Construction of River Control at Sitio Cambugtong, Brgy. Ubos, Bayawan City, Neg. Or. | Horizontal | 5000000 | Renan A. Enopia | 111 C.D. | 2018 |  |  | 0 | 0 | Temp. Suspended | 5000000
3rd District | Bayawan | Poblacion | Secondary Metering, Revamp and Installation of Distribution Transformers for Bayawan District Hospital for Two (2) Sites, Bayawan District Hospital, Bayawan City | Vertical | 1500000 | Mae Therese P. Oamilda | 24 W.D. | 2017 | 43270 |  | 1500000 | 1 | Completed | 0
3rd District | Bayawan | Villasol | Construction/Rehabilitation of Potable Water System for Brgy. Villasol, Bayawan City, Neg. Or. | Horizontal | 20000 | Renan A. Enopia | 13 C.D. | 2015 |  |  |  | 0 | For Reversion | 20000
3rd District | Bayawan | San Isidro | Construction of Deepwell, Brgy. San Isidro, Bayawan City, Neg. Or. | Horizontal | 500000 | Renan A. Enopia | 75 C.D. | 2017 | 43661 |  |  | 0.65 | For Reversion | 500000
3rd District | Bayawan | Dawis | Construction of Water Tank and Distribution Lines Leading to Dawis Community Primary Hospital, Bayawan City | Horizontal | 1000000 | John Rey C. Toledo | 50 C.D. | 2018 |  |  |  | 0 | For programming | 1000000
3rd District | Bayawan | Poblacion | Improvement of School Stage, Bayawan City East Central School, Bayawan City (Reverted from: Repair of Perimeter Fence At Bayawan City East Central School, Bayawan City - Prov'l. Sch. Board Res.# 377-2015, MOOE) | Vertical | 300000 | Mae Therese P. Oamilda | 25 C.D. | 2015 | 44565 |  | 285000 | 0.95 | Physically Completed | 15000
3rd District | Bayawan | San Isidro | Construction of School Stage at Bolirocon E/S, San Isidro, Bayawan City | Vertical | 100000 | Mae Therese P. Oamilda | 9 C.D. | 2016 | 44440 |  | 95000 | 0.95 | Physically Completed | 5000
3rd District | Bayawan | Poblacion | a) Bayawan District Jail | Vertical | 210000 | Mae Therese P. Oamilda | 25 C.D, | 2016 |  |  | 0 | 0 | For Reversion | 210000
3rd District | Bayawan | San Isidro | Completion of School Stage at Bolirocon E/S, San Isidro, Bayawan City | Vertical | 200000 | Mae Therese P. Oamilda | 12 C.D. | 2020 | 44440 |  | 190000 | 0.95 | Physically Completed | 10000
3rd District | Bayawan | San Isidro | Completion of School Stage at Bolirocon E/S, San Isidro, Bayawan City, Negros Oriental | Vertical | 200000 | Renan A. Enopia | 17 C.D. | 2021 |  |  | 0 | 0 | For implementation | 200000
3rd District | Bayawan | Poblacion | Completion of School Stage at Bayawan East Central E/S, Bayawan City, Negros Oriental | Vertical | 200000 | Renan A. Enopia | 13 C.D. | 2021 |  |  | 0 | 0 | For implementation | 200000
3rd District | Bayawan | Narra | Completion of 2CL School Building at Terong Primary School, Brgy. Narra, Bayawan City, Negros Oriental | Vertical | 400000 | Renan A. Enopia | 27 C.D. | 2021 |  |  | 0 | 0 | For implementation | 400000
3rd District | Bayawan | Poblacion | Improvement of Bayawan District Hospital, Bayawan City | Vertical | 1058584 | Mae Therese P. Oamilda | 74 C.D. | 2014 | 44039 | 44256 | 1058584 | 1 | Completed | 0
3rd District | Bayawan | Poblacion | Repair and Renovation of Out-Patient Department, Bayawan District Hospital, Bayawan City (Reverted from: Repair of Operating Room, Bayawan District Hospital, Bayawan City - SP Res.# 887-2012, 20% EDF, AIP 2013) | Vertical | 500000 | Britney A. Patajo | 37 C.D. | 2017 |  |  | 0 | 0 | For implementation | 500000
3rd District | Bayawan | Kalumboyan | Construction of seven (7) Breastfeeding Rooms to 7 CPH's, Kalumboyan, Bayawan City | Vertical | 133500 | Britney A. Patajo | 16 C.D. | 2017 |  |  | 0 | 0 | For Reversion | 133500
3rd District | Bayawan | Dawis | Construction, Upgrading, Expansion, Repair and Renovation of Dawis Community Primary Hospital, Bayawan City, Neg. Or. | Vertical | 2000000 | Britney A. Patajo |  | 2018 |  |  | 0 | 0 | For Reversion | 2000000
3rd District | Bayawan | Poblacion | Improvement of Infectious Diseases Isolation Facility, Bayawan District Hospital | Vertical | 3500000 | Mae Therese P. Oamilda | 174 C.D. | 2021 |  |  | 3500000 | 1 | Completed | 0
3rd District | Basay | Bongalonan | Construction of Rip-Rap and Retaining Wall along Tyabanan River as Flood Control Structure in Bongalonan, Basay | Horizontal | 1800000 | Renan A. Enopia | 53 C.D. | 2016 | 43878 |  | 1698246 | 0.9435 | Temp. Suspended | 101754
3rd District | Basay | Poblacion | Improvement & Rewidening of Provincial Road with Drainage Canal at the Municipal Entrance Road along the Municipal Slaughterhouse, Basay, Negros Oriental | Horizontal | 5000000 | Renan A. Enopia |  | 2022 |  |  | 0 | 0 | For implementation | 5000000
3rd District | Basay | Maglinao | Construction of Box Culvert, Barangay Maglinao, Basay, Negros Oriental | Horizontal | 2000000 | Japhet T. Pinili | 43 W.D. | 2017 | 43988 | 44021 | 2000000 | 1 | Completed | 0
3rd District | Basay | Poblacion | Additional Appropriation for the Construction of Box Culvert, Barangay Poblacion, Basay, Negros Oriental | Horizontal | 1000000 | Jun Bernard D. Cual | 28 C.D. | 2017 |  |  | 0 | 0 | For programming | 1000000
3rd District | Basay | Nagbo-alao | Additional Appropriation for the construction of Multi-purpose Evacuation Center, Brgy. Nagbo-alao, Basay, Neg. Or. | Vertical | 3000000 | Mae Therese P. Oamilda | 107 C.D. | 2018 | 44044 |  | 2910000 | 0.97 | Physically Completed | 90000
3rd District | Basay | Poblacion | Construction of Two-Storey Multi-Purpose Building, Poblacion, Basay, Negros Oriental | Vertical | 5000000 | Planning Division |  | 2023 |  |  |  | 0 | For programming | 5000000
3rd District | Basay | Olandao | Additional Appropriation for the Construction of Multipurpose Evacuation Center, Barangay Olandao, Basay, Negros Oriental | Vertical | 3000000 | Renan A. Enopia |  | 2022 |  |  | 0 | 0 | For implementation | 3000000
3rd District | Basay | Poblacion | Construction of School Fence, Basay | Vertical | 884000 | Mae Therese P. Oamilda | 121 W.D. | 2016 | 44075 |  | 848640 | 0.96 | Physically Completed | 35360
3rd District | Basay | Nagbo-alao | Improvement of Waterworks System, Barangay Nagbo-alao, Basay (Realigned from: Purchase of Road Roller for use in the Implementation/Const. of various infrastructure projs. In Basay - Php 1,800.00; SP Res. # 858-2011, AIP 2012) | Horizontal | 300000 | Japhet T. Pinili | 40 CD | 2013 |  |  | 0 | 0 | For Reversion | 300000
3rd District | Basay | Bal-os | Improvement of Waterworks System at Bal-os NHS, Basay | Horizontal | 50000 | John Rey C. Toledo | 8 C.D. | 2016 |  |  | 0 | 0 | For implementation | 50000
3rd District | Basay | Cabatuanan | Installation of Waterworks System, Barangay Cabatuanan, Basay | Horizontal | 1000000 | Jun Bernard D. Cual | 80 C.D. | 2019 | 44353 |  | 950000 | 0.95 | Physically Completed | 50000
3rd District | Basay | Nagbo-alao | Construction of Evaucation Center/Covered Court, Nagboalao, Basay | Vertical | 500000 | Mae Therese P. Oamilda | 38 C.D. | 2014 | 44090 |  | 485000 | 0.97 | Physically Completed | 15000
3rd District | Basay | Actin | a) Improvement/Construction of Day Care Center Actin, Basay | Vertical | 300000 | Mae Therese P. Oamilda | 38 C.D. | 2016 | 44105 |  | 285000 | 0.95 | Physically Completed | 15000
3rd District | Basay | Bongalonan | Rehabilitation of Multi-purpose Hall, Brgy. Bongalonan, Basay | Vertical | 50000 | Mae Therese P. Oamilda | 7 C.D. | 2018 | 43802 |  | 48250 | 0.965 | Physically Completed | 1750
3rd District | Basay | Linantayan | Additional Appropriation for the Construction of Multipurpose Evacuation Center, Barangay Linantayan, Basay, Negros Oriental | Vertical | 3000000 | Renan A. Enopia |  | 2022 |  |  |  | 0 | For Reversion | 3000000